## Sundarbans Journal
| Description of Change |  |  |  |  | Significance of change | Contributing Factors | Evidence
Partner | (Social actor - individual, groups, institutions, networks, community, organisation) | What did they do different? What was the change (Change in behaviour, relationships, actions, activities, agenda, policies, or practices) | When did it happen? (Should be after programme activities - date/month/year - specified) | Where did it happen? (Eg. Village / block / district; or - local, national etc) | Outcome Statement | Why is this observation of change noteworthy? How does it relate to the program vision and/or theory of change? | What do you think has contributed to this change? What, specifically, has the program done that might have contributed to this change? | Include links to any additional documentation or sources if relevant, e.g. news stories, speeches, meeting notes
Baikunthapur Tarun Sangha | Total 20 Farmers group from 5 villages | A total of 20 farmers' groups from 5 villages are practicing Climate Adaptive Natural Farming (CANF), disaster-resilient agriculture, and diversified farming. They have also adopted improved land-use processes to enhance agricultural sustainability and resilience. | August (Kharif & Rabi season) 2024 to January 2025 | Purba Sripatinagar, Paschim Sripatinagar villages, Choto and Boro banashyamnagar and Satyadaspur villages | During the Kharif and Rabi seasons (August 2024 to January 2025), 20 farmer groups from Purba Sripatinagar, Paschim Sripatinagar, Choto Banashyamnagar, Boro Banashyamnagar, and Satyadaspur villages have adopted and implemented climate-smart agricultural practices. They have transitioned to organic and mixed farming approaches on both their own lands and shared lands, demonstrating increased awareness and capacity to practice sustainable farming. This shift indicates a behavioral change towards climate resilience, reducing dependency on chemical inputs, and enhancing soil health and productivity. | This observation is significant because it reflects a tangible shift in farmers' behaviors and agricultural practices toward climate resilience. The adoption of climate-smart, organic, and mixed farming methods demonstrates: 1. Increased Awareness & Capacity – Farmers are actively applying sustainable farming techniques, showing that they understand the benefits of reducing chemical dependency and improving soil health. 2. Community-Led Adaptation – The shift is not limited to individual farmers but extends across 20 farmer groups, indicating collective action and peer learning. 3. Utilization of Shared Lands – The inclusion of hare (shared) lands suggests an expansion of sustainable farming beyond individual holdings, fostering resource optimization and cooperation. 4. Climate Resilience & Sustainability – By adopting organic and mixed practices, farmers are better prepared to handle climate variability, ensuring long-term food security and livelihood stability. This change aligns with the program’s vision of climate-resilient and sustainable agriculture by: • Strengthening Livelihoods – Encouraging diverse, eco-friendly agricultural practices contributes to income stability and food security. • Enhancing Environmental Sustainability – Reducing chemical use improves soil fertility, biodiversity, and water conservation. • Scaling Sustainable Solutions – The adoption by multiple farmer groups demonstrates the replication potential of climate-smart practices, paving the way for wider policy or practice shifts. • Empowering Local Communities – By equipping farmers with knowledge and skills, the initiative fosters community ownership of sustainable agricultural solutions. This observation signifies progress toward the program's broader goal—enhancing farmers' resilience against climate change while promoting sustainable agro-ecological transitions | Team members from 360 farmers conducted capacity-building programs, Chas Chakro, Kishan Pathshala, transect walks, and exposure visits, where they trained and learned from farmer group leaders on climate-smart practices. These initiatives enhanced farmers' knowledge and skills, encouraging the adoption of organic and mixed farming methods on their own and shared lands. | [Photographs of fields]
| Women collectives: Pather Sathi Women's Collective, Rubi, Sasmalpara &Sanjher Bati PAR Group members with Sarmistha womens groups | All members taken ineatatives of water congestion (water logging) in the village canal; took collective action to water remove from agriculture land by engaging with thelocal panchayat and para village committee, | Collectives afforts by 23 women members from Sripatinagar village | Sanjher Bati PAR Group action was held at Purba Sripatinagar village in Achintyangar G.P.; Pather Sathi Women's Group action was held Paschim Sripatinagar village in Achintyanagar G.P.; | In response to water congestion (waterlogging) in the village canal, all members took collective action to remove excess water from agricultural land by engaging with the local panchayat and para village committee. A significant contribution came from 23 women members from Sripatinagar village, demonstrating strong community-led efforts in addressing the issue. Additionally, the Sanjher Bati PAR Group in Purba Sripatinagar and Pather Sathi Women's Group in Paschim Sripatinagar played key roles in mobilizing local stakeholders, ensuring effective problem-solving at the community level within Achintyanagar G.P.. These initiatives highlight an improved collective decision-making process, local governance engagement, and climate resilience practices within the community. | This change is significant because it demonstrates community-led action and collective problem-solving in response to water congestion. Key reasons include: • Strengthened Local Governance – Engagement with the panchayat and para village committee shows increased community participation in decision-making. • Women's Leadership – The involvement of 23 women members highlights growing women's agency in local environmental management. • Disaster Resilience – Addressing water logging in agricultural land supports climate adaptation and food security by preventing crop damage. This aligns with the program’s vision of community empowerment and climate resilience by: • Promoting Collective Action – Encouraging group-led initiatives fosters long-term sustainability. • Enhancing Climate Adaptation – Water management efforts contribute to disaster preparedness and resilient farming. • Building Local Capacity – Strengthening community structures ensures sustainable solutions for environmental challenges. | The change was driven by community awareness, collective decision-making, and proactive engagement with local governance structures. Women’s participation and farmer group mobilization played a crucial role in taking action against water congestion. • Conducted capacity-building sessions on climate resilience and water management. • Facilitated community meetings, PRA exercises, and transect walks to identify waterlogging issues. • Strengthened women’s leadership through group mobilization and decision-making platforms. • Encouraged collaboration with the panchayat and para village committee, ensuring local governance support. • Organized farmer field schools and exposure visits to learn water management best practices. These efforts empowered the community to take collective action, improve disaster resilience, and strengthen local problem-solving mechanisms. | Case Stories, Meeting Resolution, Photos,
| Housewives ( Mixed Group); Parents of Adolescent Group members; | Significant changes have been observed in family dynamics, gender equality, and women's participation in decision-making. 1. Change in Behavior & Relationships: Families prioritize equal treatment for boys and girls in education, health, and clothing. Fathers and family heads now seek and respect the opinions of women in children’s education-related decisions. Women are encouraged to participate in training and community meetings at the panchayat and block levels. 2. Change in Actions & Activities: Girls are allowed to attend tuition and cultural programs, which was previously restricted. Women, particularly housewives, have gained financial freedom, making small expenditures at their discretion. 3. Change in Practices & Policies: Girls now use sanitary napkins instead of cloth, promoting better hygiene and health awareness. Household spending is more gender-equitable, with equal expenses on boys' and girls' clothing. These changes reflect a shift toward gender equity, women's empowerment, and improved decision-making roles for women in families and communities. | Auguest 2024 to January 2025 | Purba Sripatinagar, Paschim Sripatinagar, Choto, Boro banashyamnagar & Satyadaspur villages | Ov.er the last six months, family dynamics have shifted towards gender equality, with women gaining decision-making roles and girls receiving equal opportunities in education, health, and participation. Families now prioritize equal spending on boys' and girls' needs, and women actively engage in community activities. Improved financial autonomy for housewives and enhanced menstrual hygiene practices indicate positive social transformation towards women’s empowerment and gender equity in Purba Sripatinagar, Paschim Sripatinagar, Choto, Boro Banashyamnagar, and Satyadaspur villages | This change promoting equal opportunities for girls and women, enhancing their agency and promoting social transformation. The shift reflects the theory of change, in our project villages increased awareness, participation, and financial autonomy lead to sustainable gender-equitable practices and policies. | This change has been driven by awareness programs, community training, and capacity-building initiatives that promote gender equality and women's empowerment. The program has specifically conducted workshops, facilitated discussions, and encouraged women's participation in decision-making and financial independence, leading to shifts in family dynamics and social norms. | Case Stories, Meeting Resolution, Photos,
| Mixed Group (farmers, women and adolescents) | Collective members are taking benefits of various welfare schemes like Krishak Bandhu, Seed Support, Swasthay Sathi, Disability Pension, Widow Pension, lakshmibhandar by engaging with officials in the concerned line department; | July-2024 to onwards | Purba Sripatinagar, Paschim Sripatinagar villages, Choto banashyamnagar, Banashyamnagar and Satyadaspur villages | Collective members, including farmers, women, and adolescents, are actively accessing welfare schemes such as Krishak Bandhu, Seed Support, Swasthya Sathi, Disability Pension, Widow Pension, and Lakshmibhandar by engaging with government officials, enhancing their financial security and social protection. | It reflects increased awareness, agency, and engagement of total 356 community members in accessing entitlements, leading to improved financial and social security. It aligns with the program vision of community empowerment by ensuring equitable access to government welfare schemes, promoting resilience, and enhancing livelihoods through informed participation. | The change has been driven by continuous capacity-building efforts, awareness campaigns, and facilitation of direct engagement with government departments. The program has specifically contributed by: 1. Knowledge Building – Conducting workshops and community meetings to educate members about available welfare schemes and eligibility criteria. 2. Facilitation Support – Assisting in application processes, document preparation, and follow-ups with concerned officials. | Various documents, certificates in support of the benefits obtained by members
| Women and Adolescent Group members | Women and adolescent group members from 5 villages are actively engaged with local PRI representatives and institutional stakeholders, developing stronger relationships and collaboration. They participated in collective meetings and decision-making processes, influencing local governance and community development. This shift indicates increased agency, leadership, and recognition of their voices in local decision-making spaces. | July-2024 onwards | Purba Sripatinagar, Paschim Sripatinagar villages, Choto and Boro banashyamnagar & Satyadaspur villages | Since July 2024, representatives of local PRI and other institutions have actively participated in the meetings and observations of women and adolescent groups in Purba Sripatinagar, Paschim Sripatinagar, Choto Banashyamnagar, and Boro Banashyamnagar villages. Their engagement has strengthened institutional linkages, facilitated better access to entitlements, and enhanced the visibility and credibility of collective actions within the community. | It signifies increased institutional engagement with community collectives, developing stronger linkages between grassroots groups and local governance structures. It reflects progress toward inclusive decision-making, improved access to entitlements, and greater community participation in local development processes. This aligns with the program vision of empowering marginalized groups, particularly women and adolescents, by strengthening their agency and voice in governance structures. It supports the theory of change by demonstrating that active institutional participation leads to enhanced resource access, improved service delivery, and sustainable community-led development. | This change has been contributed by continuous community mobilization, capacity-building efforts, and advocacy initiatives that strengthened the confidence and leadership skills of women and adolescent group members. Specifically, the program facilitated structured meetings between collectives and PRI representatives, conducted training on governance and rights, and encouraged active participation in decision-making processes. Regular engagement with local institutions, awareness campaigns, and strategic networking efforts have also played a key role in fostering institutional responsiveness and collaboration. | Photos, Case stories, meeting regulation
| 5 Disaster Management Taskforce - DMTF groups | Over the last seven months under the ACV project, the 5 Disaster Management Taskforce (DMTF) groups have actively engaged in early warning dissemination, community risk mapping, and response planning. | July - 2024 to onwards | Purba Sripatinagar, Paschim Sripatinagar villages, Choto and Boro banashyamnagar & Satyadaspur villages | Since the last 7 months under the ACV project, five Disaster Management Taskforce (DMTF) groups in Purba Sripatinagar, Paschim Sripatinagar, Choto Banashyamnagar, Boro Banashyamnagar, and Satyadaspur villages have improved disaster preparedness. They have actively engaged in early warning dissemination, community risk mapping, and response planning, enhancing community resilience to climate-induced disasters. Their proactive approach has strengthened local disaster management capacities and coordination with stakeholders. | This change is significant because it demonstrates increased community ownership and preparedness for disaster risk reduction. The active engagement of Disaster Management Taskforce (DMTF) groups in early warning dissemination, risk mapping, and response planning enhances local resilience, reducing vulnerabilities to climate-induced disasters. The ACV project envisions empowered communities that proactively mitigate disaster risks and adapt to climate challenges. This change aligns with the theory of change by developing local leadership, strengthening preparedness mechanisms, and improving coordination between community groups and institutions, ultimately ensuring long-term disaster resilience and sustainability. | Capacity-building sessions, hands-on training, and regular engagement with community stakeholders have strengthened the Disaster Management Taskforce (DMTF) groups' ability to respond effectively. The ACV project facilitated training on early warning systems, community risk mapping, and response planning. It also promoted collaboration between DMTF groups and local PRI institutions, ensuring better preparedness and coordination in disaster management. | Photos, Case stories, meeting regulation, short Video
Indraprastha Srijan Welfare Society | Individual girls and women of the collectives and boys and males of the families | Change of attitude and behaviour of the adolescent girls on menstrual taboos and boys, girls, men and women on social norms | During the 2022 onwards | Paschim Sridharpur, Gurudaspur and Ramnagar Abad villages | Vulnerable communities identify key issues and take individual and collective action | Regarding menstrual hygiene and taboos, almost all the adolescent collective members are aware about the issues of menstrual hygiene. Among them, in few families they are able to break the misconceptions with positive behaviour. In collaboration with the gram panchayat they are able to stop eve teasing in their locality. Women and adolescents girls particularly and some of the boys are questioning on gender disparity in family etc. Thinking started with some changes of attitude and behaviour on the gender norms and practices. In some of the families, males and boys are supporting on the household chores like fetching drinking water, sending children to school, washing clothes and utensils, cooking etc. Five adolescents have stopped misuse of mobiles by peer pressure. Another two have reduced the uses of mobile phone to some extent, and trying to stop to use during study, as the peers have shared. | Active participation in sessions, meetings, training and workshops on regular basis on the issues as per modules following the participatory tools and technique used through which they were able to take it easily by heart. | Meetings notes, process documentation, photographs, short stories
| Adolescent boys and girls along with community people | They are meeting on a regular basis with creation of a fund for future maintenance, cleaning the surroundings of the water body. Postering on the do's and don'ts causes stopped to uses of bottles, taking bath by the villagers on tubewell platform, misuses of drinking water etc. | 2023 onwards | At the three villages of Paschim Sridharpur, Gurudaspur and Ramnagar Abad | Vulnerable communities identify key issues and take individual and collective action | This kind of thinking and initiation started and linked with the impacts of climate change by the adolescents to save water and keeping clean the water bodies. Individuals or collectives of adolescents are working on the issues of saving water and care and maintenance of water bodies like tubewell in their locality. Total eight tubewells are having water user committees. | Different sessions held on environment related issues | photographs, report and collected data, meeting resolution, WATSAN committee resolution
| Adolescent boys and girls along with community people | Regarding plastic pollution, among them twenty boys and girls are with practice of collecting the plastic carry bags from the roads and surrounding of their houses and sending to the SLWM. | During the 2022 onwards | Paschim Sridharpur, Gurudaspur and Ramnagar Abad villages | Vulnerable communities identify key issues and take individual and collective action | It was initiated by the boys and girls. The gram panchayat has also mission to make the gram panchayat plastic free. The gram panchayat is also collaborating boys and girls and becoming the part of this mission to be successful. | Different sessions held on environment related issues, specially on global warming and climate change. Rally and community awareness are on this issue being continued. | Photographs, report and collected data, meeting resolution,
| Collective action by the boys and girls collectives | Raised community awareness through wall writing on reducing child marriage and school drop out | 2021, 2022, 2023 and 2024 | Paschim Sridharpur, Gurudaspur and Ramnagar Abad villages | Vulnerable communities identify key issues and take individual and collective action | Even children also took initiatives to work on the social issues through wall writing for community awareness and action is in line with project mision. With the help of local influential person, one girl readmitted to class IX in a formal school, when her mother and elder sister forced her to give up education after informed about an affair of the girl with a boy in that time. Now the girl is regular in her study. | They were taking initiatives by their own after having acquainted from the different session on the identified social issues can be addressed by them, if they are willing to do as facilitated by the field mobilizers. | photographs and stories, resolution of the session
| Adolescent girls group | The AGs have studied and Analysed the issue of child marriage and elopment through Participatory Action Research (PAR). The process is being continued with risk analysis on the plan of activities and the steps to be followed. | October, 2022 onwards | Ramnagar Abad village | Vulnerable communities identify key issues and take individual and collective action | It is in line with the mission of the project. With the plan of activities and analysing the potential risks, they are also being ready to take the challenges, as for example, thinking to have support of influential persons, ASHA, AWWs, Panchayat Pradhan and members with them to execute their work collaboratively and successfully. | The girls collective and process followed by the collective with survey and analysis using participatory tools and technique. Thereafter, root cause analysis, stakeholder mapping etc. and then plan of action also done by them. A document is made properly and can be disseminated in different platform asking for support and cooperation to curb the situation. | Photographs and report,
| Celebration of special days - children day, international women day, world environment day, gramin mela by the adolescent, women and farmers collectives engaging the gram panchayat | They have overcome their fear, shyness, gain courage and confidence to organise the same with collective effort and whole hearted participation specially sharing their change stories of women and adolescents and telling stories as composed by the adolescents along with others. | Since 2022 onwards | Digambarpur Gram Panchayat | Vulnerable communities identify key issues and take individual and collective action | Different talents are explored. One adolescent girl representative from ISWS along with two others from Mukti and Rupantaran Foundation participated in an international conference at Jamshedpur on the 14th December, 2024 on climate change on 'Harnessing Power of Education to Embrace and Adopt green initiatives' behalf of ACV consortium. All are appreciated with their remarkable presentation. | They have got an open space to shared their views and opinion, most of them have the scope of taking part in the games, sports, role play, cultural events as they like without any barrier. Competitions are held. | Photographs and reports, stories and poems composed by the boys and girls on some issues and context.
| Women collective members make study on ICDS issues as identified by them | Village women collectively initiating a process of evidence collection on the issues of ICDS | November, 2023 onwards | In the three villages taking the information of 13 ICDS centre | Vulnerable communities identify key issues and take individual and collective action | This is the first time making a questionairre on the infrastruture and service related issues of ICDS centre, they were collecting the data interviewing with the local women and the AWWs of the centres. There was also scoring and ranking of each centre using participatory tools. again sitting with the respective AWWs the data were verified with some additions and rectification to confirm on the actual facts and figures. It would be documented by the collective members ICDS centre wise separately and shared with the stakeholders for information, and plan for solution. | The issue was raised in the para baithak and sansad sabha, then in gram sabha. But our facilitator guided by the resource organisation motivated them to collect the evidences to know the facts as necessary for taking decision by the duty bearers for the raised issues to be mitigated. | photographs, report and collected data, meeting resolution, the evidence created by the women collectives.
| Famers both men and women farmers mind set have changed towards the environment friendly and climate smart agricultural practices promoting organic farming method | farmers mind set have changed towards the environment friendly and climate smart agricultural practices promoting organic farming method. Individual action on climate smart agriculture with indigenous vegetable seed collection and preservation. | 2021 onwards | At the three villages of Paschim Sridharpur, Gurudaspur and Ramnagar Abad | Communities are resilient to climate change induced risks and disasters | 35 farmers did model nutrition garden in kharif, 36 nutrition garden in Rabi season, 32 circle bed, 10 sack culture through out the year. The collected seed are exchanged among them during cultivation. As they shared, family nutrition is being met, some women said, very small amount of money they earned from market selling the excess of vegetable produced. | Trained on eco farm management, introduction of model nutrition garden along the compost preparation, integrated pest management, it was disseminated to the famers collective members and they were influenced to do the same in a small scale. | photographs of field,
| Women farmers particularly | Individual action on climate smart agriculture with indigenous vegetable seed collection and preservation | Since 2022 onwards | Digambarpur Gram Panchayat | Communities pursue climate change - resilient livelihood practices | In the season,45 women collected and preserved the indigenous vegetable seed after prekharif and kharif and used without depending on the market. | The number of women farmers is increasing more than the previous year. | Report and photographs
| Adolescents participation and playing leading roles in sishu sansad organised by the Panchayat | They raised their voices for renovation of a canal, which is dirty and full of garbage done by the community, provision of street light, and spoken english, set up a park in ICDS centre, problem of midday meal, sanitary pad vending machine of school is not functioning, need of village road development etc. which are included in gram panchayat development plan. | 17th December, 2024 | Digambarpur Gram panchayat ground | Communities pursue access to social entitlements, schemes, and adequate services through sustained engagement with relevant duty bearers and service providers | The adolescent were with spirit of engagement and learning while going into dialouge with the panchayat representatives to inform and to be informed with their list of demands and whats are solved as submitted previously. | Before that the representatives of the adolescent collectives were having the exposure thrice with pancahayat representatives and officials, where they also learned a lot, gained knowledge, courage and confidence. | Report and photographs
| Women and farmers collective members took part in parabaithak, sansad sabha, gram sabha and women sansad and raising voices with their list of individual and collective need and requirements | The women are taking part in parabaithak, sansad sabha, gram sabha and women sansad and raising voices with their list of individual and collective need and requirements. Previopusly they were demanding for individual self need only, now they were advocating for the other needy and vulnerable and also for the village issues. Now the no. of participants are increasing more then before. | 2023 onwards | At Digambarpur Gram Panchayat area | Communities pursue access to social entitlements, schemes, and adequate services through sustained engagement with relevant duty bearers and service providers | Women were not only demanding for individual need, at the same time they were also demanding the needs of the others after discussing among themselves with cooperative mind set considering the need of most vulnerable families. Some of the items are included in the gram panchayat development plan. it is also with the mision of the project as engagement and relationship of community with panchayat made on their issues and activities. As previously demanded, the yoga centre, culvert, two village roads, tubewell at SSK made and two street light installed. | Before participating in different sabhas of gram panchayat, the collective members were preparing themselves with mutual sharing and understanding about the list of issues to placed before gram panchayat as facilitated by the field mobilizers different times prior to the gram sabhas and others. | List of issues raised, report, photographs, plan of different upasamities.
| Farmers collectives move to the office of Assistant Director of Agriculture (ADA), Krishi Vijnan Kendra (KVK), Nimpith | Got training, agri inputs and soil health card. Farmers collectives move to the office of Assistant Director of Agriculture (ADA), Krishi Vijnan Kendra (KVK), Nimpith | 2022, 2023 | all the three villages of Paschim Sridharpur, Gurudaspur, and Ramnagar Abad | Communities pursue access to social entitlements, schemes, and adequate services through sustained engagement with relevant duty bearers and service providers | For the first time they were going to take training and agri inputs from the ADA office. And for first time they also went to test soil to have the soil health card. They are submitting application to ADA for training, collecting the seed like mustard seed, khesari and maize seed for cultivation after paddy. (79 cultivated maize, 6 cultivated Khesari, 16 cultivated mustard seed). | After going into dialogue with the officials of the the relevant offices, it was possible to access. Stakeholder engagement meeting was organised and follow up took place. | photographs and reports,
| Strengthening village level child protection committee | With the support and cooperation of PRI | 2021 onwards | Paschim Sridharpur, Gurudaspur and Ramnagar Abad villages | PRI, other institutions, duty bearers and service providers support community initiatives on child safeguarding, gender equity and social norms | It is very much essential for the child safe guarding issues. Child safe guarding policy of the organisation is framed and going to be functional. Panchayat is supporting the adolescent, women on the issues to address of child protection and gender positively. Twelve village level child protection committees (VLCPC) of the four reference villages are being proactive and functional with child representatives and others. | It is guided by the resource organisation of the consotium and after having training from the District Child Protection Unit (DCPU). | Field visit and going into dialogue with the members
Mukti | Women's group | The core women group has drafted the theory of change for their own. They have set a primary objective to develop some local level strategies to prevent Gender based violence espcially domestic violence. To achieve such goal, they are sensitizing the local women on different essential concepts like gender & sex, power, socialisation, concept of gender discrimination, type of violence, patriarchy, power etc . They have targeted to reach minimum 2000 women in their GP and did basic orientation program on women | August 2024 to January 2025 | Villages - Herambagopalpur, Purba Surendranagar, Dakkhin Kashinagar, Kuemuri | Vulnerable communities identify key issues and take individual and collective action | Developing a collective vision by the community themselves itself is a very major initiative. The process of Key issues identification and prioritisation are completely done by the community. As per the ToC they are developing their own set of micro level actions to achieve their goal. The current disaster proneness condition of Sundarbans is another major contributing factor which is increasing the possibilities of more GBV. | In last few years, a long term engagement with the women core group on gender is one of the major contributing factors to make the change happen in the ground. Also other social crisis like recently occurred incident is also one of the indirectly contributing factors which influences such changes among the women | https://drive.google.com/drive/folders/1DOxswsoxNHSfcpwbQ73GMy0KP6_JnDgq?usp=drive_link
| PAR group | Through participatory action research initiative, the group has analysed the root causes of the existing vulnerability of a certain part of the river embankment. Through their collective initiative, they have successfully made the block Govt agree on installing the bamboo wave crusher to reduce excessive soil erosion at that part of the embankment. Through submission of the application and mass petition and regular follow up with the respective dept, they were successfully ensured the required actions by the Govt to protect the river embankment through sustainable local level nature based solution. | 2024-08-01 | Kuemuri mouja(Heramba Gopalpur GP) | Communities are resilient to climate change induced risks and disasters & Vulnerable communities identify key issues and take individual and collective action | This kind of community research initiative is entirely a new idea to the community, The process not only helped the community to understand the issue also it helped to build skill to analyse the collected data , this process also helped them to plan the initiative, approach , how to build strategy to enegage with relevant stakeholders, how the decision can be made based on collective opinion. This helped the community to get a sense of ownership/agency over this process. | Perspective building workshop on PAR by Praxis, Regular meetings, exposure visits by the PAR members , Facilitators effort, engagement of different members including diversed age range, different social and economical conditions. The diveresity of the group helped to bring different perspectives of that issue. | https://drive.google.com/drive/folders/1YWR-wK-gQZrqevjUN6j2g6kMDWr4w6MY?usp=sharing
| Farmer group (both female and male) | # Now the group of 60 women farmers are sucessfully running 3 community seed banks to preserve salt tolerant indigenous seeds and also regular native seeds to reduce dependency on the market in terms making free choices for different crop cultivation. # The new mangrove saplings which are grown in the community nursery have been planted at the vulnerable part of the river embankment through collective initiatives | August 2024 to January 2025 | Kuemuri, Purba Surendranagar, Heramba Gopalpur | Communities are resilient to climate change induced risks and disasters & Vulnerable communities identify key issues and take individual and collective action | Community members are gradually buillding resilience to deal the adversed situation of post disaster period. The availability of different varity seeds is the basic need to protect the livelihood as well as food security. Hence community seed banks are becoming a strong local level solutions to address complex issues like post disaster livelihood and food secutity. | Continue training on organic farnming, seed collection and preservation training. seed bank need aseessment by community, involvement of local resource person , support from panchayat members for mangrove nursery , capacity building support from the organisation, exposure visits in the DRCSC ( Gopalnagar GP field area) to get a practical understanding on establishing such community led models
| Farmers group | Organic farming training for both female and male farmers to build their capacity to convert their land to make it ready for natural/organic farming | August 2024 to January 2025 | Kuemuri, Purba Surendranagar, Heramba Gopalpur and Dakshin kashinagar | Communities pursue climate change-resilient livelihood practices | People who live next to the river are constantly struggeling to protect their agricultural lands from the impact of extreme weather events. Increased level of salinity and the absence of micro organism in the agricultural lands are leading to poor production. In this context, adopting the safe coping mechanism through natural farming practices which is providing the better sustainable & local level solution to increase production | Capacity building training, connection with the local resource person, skill development training, awareness on climate change, disaster and the connection between climate change and impact on livelihood
| Youth, adolescents and women | Community level awareness programs to generate awareness on gender discrimination, menstruation related taboos, child rights and violation of CR, role responsibility, sexual abuse with children | August 2024 to January 2025 | Kuemuri, Purba Surendranagar, Heramba Gopalpur and Dakshin kashinagar Krishna chandrapur | Adult, youth, and adolescents recognise gender norms and redefine towards gender equality | Community identified the issues and raised their voice by their own, all the initiatives were majorly planned and organised by the community members with a very little support of the field members, Through these initiative they are able to reach larger number of the community people and raising basic awareness on the respective issues | Perspective building workshop, reflections , multiple meeting to discuss about diffrent social issue and how it is rleted to gender. child rights and gender related awareness , capacity building training , Praajak Module on Child rights
| Engagemnent with local stakeholders | Addition of urgent community based issues in Gram Panchayat Development Plan and successful completion of such plan by the local Govt | August 2024 to January 2025 | Kuemuri, Purba Surendranagar, Heramba Gopalpur and Dakshin kashinagar | Communities pursue access to social entitlements, schemes, and services through sustained engagement with relevant duty bearers and service providers | The active participation of the community in the process of GPDP is creating larger scope for future to develop a sustainable standard mechanism to amplify the collective voices to ensure long term solutions | PRI training by NCAS, NCAS fellowship training, leadership training, capacity building for proper evidence generation
NCAS | Felllows | Commitment to partipisate in the fellowship program | 18-19 September, 2024Introductory workshop of the fellowship program | South 24 Pargana | Clarify Purpose and Scope: Introduce the fellowship program to ensure all participants understand its purpose, scope, and responsibilities. Foster Team Bonding: Develop strong team bonding among the fellows, enabling them to collaborate effectively as a cohesive team. Identify Work Interests: Identify each fellow's specific work interests and organize them into groups based on these interests. | Commitment to participate in the felloship program is the acceptability of two facts 1st. decision to make change for the common goods in the community and 2nd. they need to learn to bring the change | - Curated workshop designed to introduce the fellowship program and activitties like act on the community issues, games, reflections etc | Pic, Prgram schedule, program reports,
| Fellows | Prepared the strategic influencing plan for the issues they were concerened with Decision to work under the know your sundarban initiatve | 13-15 November 2024 | South 24 Pargana | Understanding strategic influecning planning and iplementation | Fellows can understand the root casue of problem, identify stakeholders, SWAP analysis, and activites needed to bring desired change in the community | Exercise related to problem tree tool, stakeholder mapping, Develop action plan, and developing starategic influcing plan for the real life issues of the community Initated Know your sundarban, underwhich fellows decided to prepare year long caleder of crop, disaster, heath issues, and fishing | Program schedule, Event Report, Pics, startegic influencing plan prepared by fellows
| Fellows | Decision to engage with Local Governance Mecnanism | 03-05 Jan 2025 | South 24 Pargana | To introduce fellows to the key components of India’s governance system, including the roles of electoral representatives, the executive, and the judiciary. To provide insights into the functioning of Panchayat Raj and their significance in promoting participatory democracy at the grassroots level. Encourage Citizen Engagement: To highlight the importance of systematic citizen involvement in governance processes to drive community-driven change. Build Practical Knowledge: To equip participants with the skills and understanding to navigate governance mechanisms and advocate for effective policies and practices. | Systematic understanding of Local self Government, tools and spaces of engagment with it | Detailed functioning process of Gram Panchayat, spaces of the engagement, Budgeting process of GP etc. This was explained through real life expample of wrting letters to GP about concerned issues in the community. | Program schedule, Event Report, Pics, startegic influencing plan prepared by fellows
| Fellows | Use the acqured skills to take up the village issues in groups such as river embankment, village sewage , etc | 30 Jan 2025 to 1st Feb 2025 | South 24 Pargana | Equip fellows with skills to engage in clear, culturally sensitive, and persuasive communication. Develop active listening and public speaking techniques to effectively convey messages. Build an understanding of the principles of community mobilization and the importance of participatory approaches. Train fellows to identify community priorities, build trust, and create inclusive spaces for dialogue and action. Provide tools for conflict resolution, consensus-building, and negotiation within diverse and dynamic community contexts. Foster peer-to-peer learning and collaboration to sustain mobilization efforts beyond the workshop | communicaiton is the significant tool for communiry workers, this wrokshop taught them communicaiton techniques for the change in the community | Practical expample of communicaiton skills through real life example | Program schedule, Event Report, Pics, startegic influencing plan prepared by fellows
Prajaak
Praxis
Rupantaran Foundation | Adolescents Group | 1.They have taken part in the panel discussion by WBCPC on " including the studies of Environment and climate change as part of the syllabus" 2.They had participated at a conference held in Jamshedpur by DBMS where they presented the effects of Climate Change in the Sundarbans. 3.One of the adoloscents have been awarded the Birangana Award from the WBCPC for their commendable contribution to their community. 4. The adolescents girls have taken active participation in Breaking all Gender streotypes by taking part in the Sports for Gender Advancement- Hok Kabaddi and initiatives that was also supported and encouraged by DCPU via. their presence | 1.11/07/2024. 2. 13th and 14th December. 3. 20th December 2024. 4. 5th February, 2025 | 1. Block. 2.Jamshedpur. 3. State level. 4. Block level | Adolescent groups, equipped with knowledge and leadership skills, actively represent their climate-related issues at the block level and national platforms, influencing policy discussions and decision-making processes. Their lived experiences and insights drive meaningful dialogues on the intersection of climate change, child protection, and gender justice. Through collective advocacy, they contribute to shaping community-based climate adaptation strategies, ensuring that adolescent voices are recognized and integrated into broader climate resilience frameworks. | This change is noteworthy as it shows adolescents shifting from passive recipients to active agents of change, advocating for climate issues at block and national levels. It reflects increased awareness, confidence, and leadership, aligning with the program vision of fostering adolescent agency. It validates the theory of change that equipping adolescents with knowledge, skills, and platforms enables them to influence policies, challenge harmful practices, and contribute to community resilience. Their representation strengthens advocacy efforts, ensuring grassroots realities shape systemic responses to climate change and child protection. | This change has been driven by capacity-building initiatives, leadership training, and advocacy skill development for adolescents. The program has facilitated perspective-building sessions, peer collectivization, and engagement with stakeholders, enabling adolescents to articulate their concerns confidently. Additionally, life skills training and exposure to policy dialogues have enhanced their ability to represent climate-related issues. Consistent mentoring, access to platforms for expression, and the creation of safe spaces for discussion have also played a crucial role in empowering them to advocate at block and national levels.
| Women's Group | They have taken active participation in the Gender Study Circle. | November | Villages level and hub level | Women participating in the Gender Study Circle are actively engaging in knowledge-sharing and dialogue on gender issues, strengthening their understanding and collective voice. Through these discussions, they are challenging gender norms, advocating for their rights, and fostering awareness within their communities. Their active participation in disseminating knowledge empowers other women and girls, creating a ripple effect that promotes gender equity and social change at both household and community levels. | It contributes to our outcome of promoting sexual and reproductive health among women. These villages have low literacy, awareness and accessibility of health care centres due to their remote location | This change has been driven by regular Gender Study Circle sessions, where women engage in discussions on gender norms, rights, and social structures. The program has facilitated safe spaces for dialogue, perspective-building exercises, and knowledge-sharing activities, enabling women to articulate their experiences and insights confidently. Additionally, capacity-building workshops, peer learning, and mentorship support have strengthened their ability to lead discussions and disseminate knowledge. By fostering collective reflection and advocacy, the program has empowered women to challenge societal norms and drive change within their communities. | 1. Records from the Circle meets
| VLCPC | The budget for the GPDP in aspect to addressing on the issues of the child rights has been accepted and is being processed for implementation | 2024-04-01 | village level | Outcome Statement: The budget for the VLAP, focused on addressing child rights issues, has been accepted and is now in the process of implementation. This marks a significant step toward institutional commitment and resource allocation for child protection and welfare. With the approved funding, targeted interventions can be effectively executed, ensuring better safeguards, services, and support systems for children at risk. | This observation of change is noteworthy because it reflects a concrete commitment to child rights by securing resources for action. The acceptance and processing of the GPDP budget demonstrate institutional recognition of the issues raised, ensuring that child protection measures move from planning to implementation. This aligns with the program vision of strengthening community-led child protection mechanisms and validates the theory of change that when communities, especially local structures like the Village-Level Child Protection Committee (VLCPC), are empowered with knowledge and resources, they can advocate effectively for children's rights. The VLCPC's role in identifying key child protection concerns, influencing the VLAP, and ensuring accountability has been crucial in this process, reinforcing the importance of grassroots participation in systemic change. | This change has been driven by advocacy efforts, capacity building, and community mobilization led by the program. The program has facilitated training sessions for the VLCPC, enabling them to identify child protection concerns and advocate for resource allocation. Additionally, stakeholder engagement meetings and technical support have strengthened the proposal and negotiation process for the VLAP budget. By equipping local committees with knowledge, tools, and a platform to voice concerns, the program has ensured that child rights issues are prioritized, leading to budget approval and steps toward implementation. | records of the VLCPC meeting
Aangan | Community Resource Group (CRG) | CRG members are attending the platform of 4th Saturday meeting (a platform involving multi-stakeholder at local level) on a monthly basis, sharing their concerns/findings, requesting for action | Started between August '24 to October24, continuous engagement | 146 GPs across 16 blocks of N24P and S24P | Communities in the Sundarban participate in planning, decsion-making and other key processes of the local self governing bodies. They present their needs and challenges and ensure that those are followed-up and addressed. | The issue of child protection is getting institutionailized within the local goverance system. The community representatives are raising their concerns (specifically on child safety and protection issues) in the GP level platforms on a regular basis. | Continuous input and support to the CRG members helped to build their perspective. | Meeting minutes, field notes
| Gram Panchayats (GPs) | GP included the topic of "child safety and protection" as an issue of discussion in the 4th Saturday meeting (multi-stakholder meeting). | Started between August '24 to October24, continuous engagement | 146 GPs across 16 blocks of N24P and S24P | Local and district level institutions adopt policies, procedures and practices on child safeguarding. | As GP included the issue of child protection in their existing multi-stakeholder platform, all the aspects around it are getting addressed. Identification, reporting, planning and response improved a lot. | Conversation with GP on the importance of issue child protection, change in their perception | Meeting minutes, field notes
| Gram Panchayats (GPs) | GP Pradhan set up a system of supervision for the children within their jurisdiction. GP involved all local stakeholders (like local gram Sansad members, ASHA, Anganwadi Workers, Village Resource Person etc.) in this supervision system. Within this system, all aforesaid local stakeholders are engaged in the regular monitoring of the wellbeing of children of the area. This activity is incorporated as one of the agenda of FLWs during their regular home visit. As a protocol, they will immediately report to GP authority if any child risks found. | Started from October '24 | 113 GPs across N24P and S24P | Local and district level institutions adopt policies, procedures and practices on child safeguarding. | GP as a local administrator involved different stakeholders for monitoring of child safety and well-being issues. It is a major step towards system establishement / accountability in regard to GPS. |  | Meeting minutes, field notes
| FLWs ( ASHA, AWWs) | FLWs started monitoring of well-being of children duirng their regular home visit. They identified child risks (like school irregular and drop-out, child marriage) and reported to GPs | December '24 onwards | 67 GPs across N24P and S24P | Panchayati Raj Institutions, other institutions, duty bearers and service providers support community initiatives on child safeguarding, gender equity, and social norms. | The entire of ecology of the child is getting activated which led to close supervision of well-being of children. | Regular dialogue on child safety and protection in GP involving various stakeholders | Field notes
| Community Resource Group (CRG) | The CRG members identified the issue of sexual harrasment by a group of boys while the girls are returing from schools. They informed the GP and requested for action. | November '24 | Gabberia GP of Mandirbazar Block of S24P | Vulnerable communities identify key issues and take individual and collective action | The community representatives could identify the risk for children and can report to the GP seeking action. |  | Field notes
| Gram Panchayats (GPs) | As identified by CRGs, GP appointed civic police infront of school to ensure safety of girls. | November '24 | Gabberia GP of Mandirbazar Block of S24P | Panchayati Raj Institutions, other institutions, duty bearers and service providers support community initiatives on child safeguarding, gender equity, and social norms. | GP recognized work of CRGs and started taking action in response to the identified risks. |  | Field notes
| Communities and Gram Panchayats (GPs) | The community people informed GP Pradhan about two cases of child marriage which are going to happen. GP Pradhan visited the families and averted the marriage through negotiation. | December '24 | Sridharnagar GP of Patharpratima block of S24P | Vulnerable communities identify key issues and take individual and collective action | Communities are able to identify the risks and empowered to raise the issue to the local govt. On the other hand, GP is also taking actions in response to the community's request. |  | Field notes
Local and district level institutions adopt policies, procedures and practices on child safeguarding.
| Community Resource Group (CRG) | CRG members identified 5 children who engaged in work on part-time basis and completely irregular at school. They viisted the families and negotiated with the family members. | November '24 | Dakshin Roypur GP of Patharpratima block of S24P | Vulnerable communities identify key issues and take individual and collective action | CRGs identified the risks in the community and started taking action to prevent those. |  | Field notes
| Community Resource Group (CRG) | CRG members identified 17 child marriage cases and visited the families to do negotiation with the family members. | January '25 | 5 GPs of N24P and 11 GPs of S24P | Vulnerable communities identify key issues and take individual and collective action | CRGs identified the risks in the community and started taking action to prevent those. |  | Field notes
| Gram Panchayats (GPs) | Pradhan nominated Nari-o-Sishu-Sonchalok as accountable person to run this kiosk/helpdesk (Kiosk is a space (physical or virtual) set up and run by the GP authority to support children. Financial as well as human resource is being allocated to this. This will be available for children where they can get information, report their concerns and get support in repose to the reports. ). This space will be functional 2 days a week and they kept one register (or complaint box in couple of GPs) in which the adolescents can write their concerns. GP authority also organized micing to make people specifically children aware on this helpdesk where they can reach out to get support. | January '25 onwards | 26 GPs across N24P and S24P | Local and district level institutions adopt policies, procedures and practices on child safeguarding. | GP is putting a mechanism / system in place with the aim of prevention of child risks/harms |  | Field notes and the physical space at GP
| Gram Panchayats (GPs) | GPs earmarked fund for child portection activities in the GPDP for 2025-26. | December '24 and January '25 | 6 GPs of Sagar block of S24P | Local and district level institutions adopt policies, procedures and practices on child safeguarding. | GP understood and ackowledged the importance of child protection and therefore planned to earmark fund for the same. |  | Meeting minutes, field notes
Liver Foundation
Deutsche Welthungerhilfe | Youth and Women 18-35 (+ 5 years) Years of Age Group, the resident of Sundarban Island catering selected vulnerable gram panchayat in South & North 24 Parganas | Total 695 Youths including femal completed their training in different trades, out of them 174 started their micro-enterprise for income generation and their income increase is reported in the range of 5-10%. (income change data are captured only after 6 months-9 months) of a training batch completion). There has been a positive attitude towards managing their own enterprises amongst trained youth and some livestock has also been purchased, shelters for livestock has also been constructed by few trainees as part of their micro enterprises and feed for livestock has also been produced by them. Also, the awareness and participation level of trainees in differenet programmes and trainings conducted has increased. | Till December 2024 | Durbachati, Gobardhanpur, Acintanagar, Banashyamnagar in Patharpratima Block, Frezerganj in Namkhana Block, Madhusudanpur in Kakdwip Block under South 24 Parganas and Malekanghumti, Kalitala, Jogeshganj, Samsernagar, Kanaikati in Hingalganj Block under North 24 Parganas | Within December 2024, 695 youths got their training on different livelihood related trade, .e.g. Goat Keeping, Hen Rearing, Pond base Fish Farming, Organic Vegetable Farming out of them 174 started their micro-enterprise for income generation and their income increase is reported in the range of 5-10%. (income change data are captured only after 6 months-9 months) of a training batch completion). | It contribute to the develoment of livelihood and increase in their income level and hence is significant | Proper planning and initiavive of the project team | Training Records/Database of trainees, photos, videos, success stories, minutes of the meetings, reports
|  | Out of trainees, youth and women formed 4 FIG (Farmer Interst Group) and opened their bank account with the help of Government Organisation (Asst Director of Agricutlure, Fishery Extn Officer) | Till December 2024 |  | 174 Potential Rural Youth selected who are already started their entrepreneurshi initiative (4 FIGs are represented from amongst these 174 potential trainees) | It contribute to the regular followup and monitoting of the programme and proper mentoring for the development of the micropreneur and hence is significant | Close monitoring and EDP inputs to the trainees, liasion with the line departments have been facilitated by the project team | Phocopy of the resolution for the formation of FIG
Water for People Ackvo
TDH | The teaching staff in Bali Dhanamani Model High School | Introduced 'Moner Kotha' box to create a space for children to express their feelings/concerns confidentially | 2025-01-01 | Bali 2 GP, Gosaba | The teaching staff in Bali Dhanamani Model High School introduced a secure concern box in the school premises called 'Moner Kotha' for children to express their feelings and concerns confidentially and anonymously thereby creating a non threatening space for children to voices their opinions in Jan 2025 at Bali 2 Gram Panchayat in Gosaba. | This is significant because this is a stepping stone towards creating safe spaces in schools where children can voice their feelings/concerns; creating future avenues for identifying further interventions to ensure their wellbeing. It is also reflective of the school identifying the children as active agents and prioritising their voices, building a relationship of trust between teachers and students. | Animator from Praajak conducted multiple discussions with the school authorities and the children to identify the need of installation of Moner Kotha box from Nov 24 to Dec 24 in Bali 2 GP in Gosaba. | Photographs, meeting minutes, consultation reports
| Teachers and headmaster from Baikanthapur High School | identified the need for enhancing the awareness of students on suicide prevention and approached partner organisation (BUP) to conduct a suicide prevention awareness session for 112 students, which was conducted in consultation with the Anwesha Counsellor. | 2024-09-01 | Maipith Baikanthapur GP, Kultali | The school management and teaching staff of Baikanthapur High School identified the need for enhancing the awareness of students on suicide prevention and approached partner organisation (BUP) to conduct a suicide prevention awareness session with the students in Sept 2024 at Maipith Baikanthapur GP in Kultali. The session was conducted for 112 children, in consultaition with Anwesha Counsellor, creating a bridge between the school and the Counsellor for further such initiaitves to support mental health and psychosocial needs of children. | This is significant because it reflects the growing recognition and initiative of schools to identify and support the mental health needs of children, corresponding to one of the pillars of our theory of change that is to enhance the capacity of schools to support psychosocial wellbeing of children. This concern came from the teachers after a student had attempted suicide from their school and discussion between students and teachers where growing thoughts of self harm among children became aparent. | Tdh and BUP conducted series of initial discussions with the school on the importance of mental health of children from August 24 onwards.Therefore, when the incident occurred, the school immediately sought support for the conduction of an awareness session. | Request Letter from School, Report and photographs of session
| 30 children in Baikanthapur High School | During Disaster Risk Reduction drills and simulation sessions, children highlighted the unavailability of sanitary napkins in schools and flood shelters and inaccesibility of washrooms in schools as major challenges. This feedback was acknowledged by school teachers. | 2025-01-01 | Maipith Baikantapur GP, Kultali | During Disaster Risk Reduction drills and simulation sessions in Baikanthapur High School, 30 children highlighted the unavailability of sanitary napkins in schools and flood shelters and inaccesibility of washrooms in schools as major challenges, which was duly acknowledged by school teachers. | This is significant because initially the students did not share their needs, which also made the teachers believe that the perspectives and needs of children align with adult understanding of children's needs. During the sessions, when children expressed and vocalised their needs, it also meant that teachers listened to them, acknowledged it and made a note of it. Additionally, this is linked with a corresponding pillar in the theory of change to enhance the capacity of children to address their needs and vulnerabilities exacerbated by climate change. | Animator from BUP conducted Disaster Risk Reduction drills and simulation sessions in school where children and teachers were brough together as active participatnts. | Session report, photographs
| Teachers in Katamari Churamani High School, Kultali | The teachers identified the case of young girl who had stopped coming to school due to early marriage and referred the case to BUP. During home visits, BUP spoke to the child (who has now been brought back to the natal family) and her family members, and through multiple discussion, despite stiff oppositions, the girl was re-enrolled in the school, with the teachers supporting her to adjust and pursue her education. | 2025-01-01 | Deulbari Debipur GP, Kultalli | The teachers in Katamari Churamani High School identified and referred the case of young girl who had stopped coming to school due to early marriage. Based on successful referral and case management, the the girl was re-enrolled in the school in January 25 in Deulbari Debipur GP in Kultalki, with the teachers supporting her to adjust and pursue her education. | The child's return to mainstream education not only reduces her vulnerability to harm and child rights violations but also empowers her to shape her own future. The role played by the teachers is integral in this, for they not only reported but also are providing support for re-integration. | Discussions with the school (including teachers) on how partners can support them to support the mandate of schools, safeguarding training of teachers, case management and home visits at the child's house and discussions with parents to re-integrate the child into formal school | Case management log, meeting minutes
| 25 children in Palpur Adashya Vidyapeeth High School | During the sessions on gender module 25 children openly shared real-life observations of children from their villages being trafficked or engaged in child labor with the animators, connecting these experiences with the session activities. | 2025-01-01 | ShambhuNagar GP, Gosaba | 25 children in Palpur Adashya Vidyapeeth High School in Shambhu Nagar GP in Gosaba, shared real life observations of children from their villages being trafficked or engaged in child labour with animators, during the sessions on gender connecting their experiences with session activities. | This significant because as part of resilience building, we aim to enhance the adaptive capacities of children, an indicator of which is children recognising harmful social and gender practices and norms, vulnerabilities, etc. | Structured sessions were conducted based on the gender module in schools. So far, the first four sessions have been delivered on self-awareness, expression, team building etc; Based on these, children could connect the idea of exclusion with the impact of trafficking. | Session report
| Teachers in Satyanaraynpur ShashiBhushan High School and Palpur Adarsha Vidyapeeth | In two schools of Gosaba, teachers found the Sports for Protection Methodology highly engaging and encouraged the children to take the initiative to conduct sessions using the methodology, which were recognised and rewarded by certification | 2024-12-01 | Bali 1 GP and Sambhunagar GP in Gosaba | 30 students were encouraged and given certificated by their teachers in recognition of their participating inthe Kabaddi sessions organised through the Sports for Protection Methodology in Satyanaraynpur ShashiBhushan High School and Palpur Adarsha Vidyapeeth in December 24 in Gosaba. | This is significant because it is reflective of schools taking active interest in the adoption of the sports for protection methodology in their school curriculum, which is focused on enhancing the mental health and psychosoial wellbeing of children (adolescents). The active support of the teachers also eases the ability, willingness and acceptance with which the children are able to participate in the sessions. Additionally, the support of teachers is critical for the sustainability of the initiative. | Meetings with school to explain the methodology and its importance. Formation of Kabaddi groups with students from Kanyashree Clubs and Child Cabinets, and conducting sessions with children. Orienting teachers on the methodology. | Meeting minutes
| 10 schools | School teachers have actively referred 18 cases of irregular school attendance and potential child marriage to partner organisations to support children's reintegration and continuation into mainstream education, reflecting increased knowledge and confidence in identifying and addressing child protection concerns. | Nov 24 - Jan 25 | Kultali and Gosaba | School teachers have actively referred 18 cases of irregular school attendance and potential child marriage to partner organisations to support children's reintegration and continuation into mainstream education, reflecting increased knowledge and confidence in identifying and addressing child protection concerns across 10 government schools in Gosaba and Kultali between Nov 24 to Jan 25. | This is sigificant because increased reporting and safe referrral reduces the vulnerabilities of children at risk of harm, abuse, and exploitation from further aggravation. Additionally, it demonstrates teachers being able to identify, understand and act upon their duty towards child protection. | Meetings with school management committee to inform them how partner organisations can support the mandate of the schools towards safety, safeguaridng and protection+ Training of school teacher and ICDS workers on safeguarding and safe referral pathways in Feb 24 under the project. | List of cases shared by school, home visit reports
| Panchayat level disaster management committee members | The Gram Panchayat members included a project staff as a member of the Gram Panchayat-level Disaster Management Unit to bring in a child protection lens. | 2024-10-01 | Rangabelia GP, Gosaba | A field staff from the implementing partner has been nominated and included in the Gram Panchayat Disaster Management Committee b the panchayat members to bring in technical experitise of child protection in disaster management plans at thepanchayat level in Rangabelia GP in Gosaba. | It is significant because it the initiative of the Gram Panchayat demonstates its acknowledgement that a child protection lens in disaster management is important and missing. It is a step towards creating adult allies who champion the cause of child centered climate change lens. It further creates avenues for subsequently integrating child leaders themselves into the committee to represent their needs and voices. | Tdh and Praajak has conducted several meetings and consultations with panchayat members and Joint BDO to present the need for child centricity in climate change, project objectives and their expected roles in conjunction with the government frameworks and mandates from Jun 24 onwards. | Meeting minutes
| 1 ICDS supervisor | In Kultali Block, 1 ICDS Supervisor persuaded the Child Development Project Officer (CDPO) to organize a safeguarding training for all ICDS Supervisors and Workers. | 21st Jan 25 | Kultali | In Kultali Block, safeguarding trainings for ICDS workers could be successfully organised due to the persuation of an ICDS Supervisor, who relentlessly advocated with the Child Development Project Officer (CDPO) to permit all ICDS Supervisors and Workers in the block to participate in a safeguarding training organised under the project. | This is significant because initiatlly the CDPO had not allowed for the training of ICDS workers considering the number of training sessions organised by them, hindering their ability to allocate time to the centres. However, the concerned ICDS supervisor had attedned a school-level event organised under the project and recognized its distinct approach compared to other block-level initiatives; which convinced her to advocate with the CDPO to permit the training. Additionally, Taking the initiative herself, she invited all ICDS workers to participate in the training. | The project had conducted a Gram Panchyat level Shishu Sansad Sabha in Kachiamar High School in collaboration with Merigonj 1 Panchayat which the ICDS worker has attended. The participatory nature of the event along with the topics discussed motivated the ICDS worker. | Event Report, Acknowledgement from School Inspector and CDPO regarding the trainings of ICDS workers
| 6 GP | The Gram Panchayats have integrated and allocated budget for child friendly initiatives like campaign against child marriage and child labour, child friendly schools, addressing issues of children with disability, awareness regarding VLCPCs, installation of street lights, installation of sanitary pad vending machine in school into the Gram Panchayat Development Plan (GPDP) under the "Child-Friendly Village" theme across six Gram Panchayats in these blocks. | Nov-Jan 24 | Merigonj 1. Jalaberia 2, Gopalganj in Kultali; Rangabelia GP,Pathankhali GP, Bipradaspur GP in Gosaba | 6 Gram panchayats integrated and allocated budget for child friendly initiatives like campaign against child marriage and child labour, child friendly schools, addressing issues of children with disability, awareness regarding VLCPCs, installation of street lights, installation of sanitary pad vending machine in school into the Gram Panchayat Development Plan (GPDP) under the "Child-Friendly Village" theme across six Gram Panchayats in Gosaba and Kultali. | Incorporation of child-friendly theme-based activities (GPDP) into local governance planning, ensures sustained commitment to child rights and protection in six grampanchayats of the two blocks. | Tdh an implementation partners facilitated multi-stakeholder dialogues with Joint BDO and grampanchayat, children to reinforce the child protection mechanisms. The implementing partners worked closely with the gram panchayat members to develop the action plans which were submitted to the Joint BDO. Upon submission, the Joint BDO validated these plans vis email to the the Gram Panchayat. The implementation team further helped enhance the accessibility of these plan among the gram panchayat members by trnaslating it in bengali. | GPDP Action Plans, acknowledgement letter of GP
| 7-10 children | Participated during the GPDP development meeting to highlight the lack of safety due to absence of street lights in certain pockets. This was incorportated by the GP in their GPDP plan with the commitment to install street lights in the designated areas. | Nov-Jan 24 | Rangabelia GP | 10 children from the high school participated in the GPDP development meetings to highlight their issues such as lack of safety due to absence of street lights in certain pockets in Rangabelia GP. This was incorportated by the GP in their GPDP plan with the commitment to install street lights in the designated areas. | Incorporation of child-friendly theme-based activities (GPDP) into local governance planning and budgeting, ensures sustained commitment to child rights and protection. | Tdh and partners facilitated multi-stakeholder dialogues through Gram Panchayat Level ShishuSansad Sabha, including children, Panchayati Raj Institution, school teachers, health workers, ICDS and community leaders, to reinforce child protection mechanisms | GPDP action plan of Rangabelia GP
DRSC- Sunderbans | Women Farmer groups | Implemented climate smart agricultural practices | September 2024 To February-2025 | 4 Villages of Gopalnagar GP ( Uttar Gopalnagar, Dk. Gopalnagar ,Mahendranagar and Durgagobindapur ) | During the Late Kharif and Winter season (September 2024 to February 2025), 26 farmer groups comprising 405 members implemented various climate-smart practices on their farms. These included the conservation of indigenous seeds, the use of bio-fertilizers and bio-pesticides, cow urine, and other sustainable techniques. | This is significant as it directly contributes to building climate resilience among farmers. | Team members and all Community Mobilizer conducted capacity building programmes, where they trained leaders of farmer groups on climate smart activities | Training or Meeting Minutes, HHs activity and Photograph
| Adolescence Boys and Girls | Adolescent boys and girls enhance their knowledge about climate change and its impact. Adolescent girls prioritize and assert their needs while also developing the ability to resist domestic violence within their families. | September- 2024 to February-2025 | Villages of Harekrishnapur , Durgagobindapur and Mahendranagar | During the months of September 2024 to February 2025, adolescents identify their challenges and risks related to climatic hazards and violations of child rights through body mapping and mind mapping exercises. | They actively participate in Child Sansad meetings and motivate other students in their school to raise awareness about climate change. | The project coordinator and community mobilizer sensitized young boys and girls on these critical issues. | Minuts ,Photograph and their frainds meat.
| Stakeholder Meat | GP level member and community leadder | September- 2024 to February-2025 | Gopalnagar GP Office | Vulnerable communities identify key issues, select priorities, take individual and collective action, and maintain the mangrove plantation established in the area to ensure a stable riverbank and habitat for the riverbank community. | GP iniciative to developed activity plan with the involve of community through GPDP and Sansad Sava . | Team members and all Community Mobilizer conducted capacity building . | Training or Meeting Minutes, HHs activity and Photograph
| Fellowship Iniciative | Fellow leaders take responsibility for solving community problems by participating in the Gram Panchayat Development Plan (GPDP) and engaging in negotiations with local governance bodies. | September- 2024 to February-2025 | 4 Villages of Gopalnagar GP ( Uttar Gopalnagar, Dk. Gopalnagar ,Mahendranagar and Durgagobindapur ) | From September 2024 to February 2025, community members have changed their outlook and are actively engaging in advocacy with the local government to address various issues, such as canal excavation, riverbank protection, and livestock vaccination. | Fellow members conduct meetings with the local community for data collection and issue identification, while also corresponding with local government authorities. | NCAS and community mobilizers conducted capacity-building sessions, training group leaders to take positive initiatives. | Minuts ,Photograph and their frainds meat.
| Movement of Community Resource Persons | Community Resource Persons (CRPs) enhance their knowledge of climate-smart agriculture and sustainable livelihoods. | September- 2024 to February-2025 | 4 Villages of Gopalnagar GP ( Uttar Gopalnagar, Dk. Gopalnagar ,Mahendranagar and Durgagobindapur ) | From September 2024 to February 2025, CRPs have been providing community members with capacity-building training on various climate-adaptive alternative livelihood models. | CRP members visit neighboring houses and village-level communities to promote the development of nutrition gardens, seed collection, and the use of different pest control methods. | DRCSC and community mobilizers conducted capacity-building sessions to train CRPs in taking positive initiatives. | Training or Meeting Minutes, HHs activity and Photograph
| Gender study Circale | The program ensures that the concept of violence includes various forms of gender-based violence, such as domestic violence, sexual violence, acid attacks, honor killings, sexual trafficking of women, female genital mutilation, and child, early, and forced marriage. | September- 2024 to February-2025 | 4 Villages of Gopalnagar GP ( Uttar Gopalnagar, Dk. Gopalnagar ,Mahendranagar and Durgagobindapur ) | From November 2024 to February 2025, Gender Study Circle representatives raise awareness in their communities about gender discrimination and domestic violence. |  | Rupantaran Foundation and community mobilizers conducted capacity-building sessions, providing training on gender-related issues. | Minuts ,Photograph and their frainds meat.
Kamonohashi
IPAS

## Tea Garden Journal
| Description of Change |  |  |  |  | Significance of change | Contributing Factors | Evidence
Partner | (Social actor - individual, groups, institutions, networks, community, organisation) | What did they do different? What was the change (Change in behaviour, relationships, actions, activities, agenda, policies, or practices) | When did it happen? (Should be after programme activities - date/month/year - specified) | Where did it happen? (Eg. Village / block / district; or - local, national etc) | Outcome Statement | (Why is this observation of change noteworthy? How does it relate to the program vision and/or theory of change?) | What do you think has contributed to this change? What, specifically, has the program done that might have contributed to this change? | Include links to any additional documentation or sources if relevant, e.g. news stories, speeches, meeting notes
Pratham | Youth from Tea Gardens | Youth develop industry-relevant practical, theoretical, and soft skills, improving their employability across various sectors. This comprehensive training equips them with the knowledge and abilities needed to succeed in diverse professional environments and career paths. | After the training of 45 days | Training conducted in the center and provided placement in different parts of the country. | Tea garden workers explore alternative livelihood options in the formal economy, supported by industry linkages, financial resources, and support systems, reducing their reliance on tea gardens as their primary source of income. | Tea gardens face the risk of closure, which could result in significant job losses and economic uncertainty for workers. Additionally, the low wages in tea gardens make it challenging for workers to meet their household expenses and basic needs, increasing their financial vulnerability. | Mobilization: Building awareness about vocational education through community engagement activities. Collaborating with local stakeholders, including community leaders, Aanganwadi/ASHA workers, and parents, to encourage youth participation in skilling programs. Training: Awareness: 2-7 days of self-learning courses introducing the trade. Foundation Skills: 15-25 days of virtual or in-person instructor-led training to develop core technical skills. Practical Skills: 20-30 days of hands-on training conducted at Pratham centers, industry partner locations, or community-based Ustaad spaces. This hybrid model combines digital content, video calls, and practical sessions. Placement: Connecting trainees to jobs, offering interview preparation, and leveraging a network of 7000+ industry partners. Post-Placement: Regular follow-ups, job retention support, alumni networks, social media engagement, and a toll-free helpline (10 am-7 pm, weekdays). | Enrollment Forms, MIS Data, Offer Letter for Placement
| Youth and their family | They chose the alternative form of livelihood from traditionally followed livelihood practice i.e. working in Tea Garden as unskilled labour. They retrain in their jobs after placement. | From August 2024 to January 2025 | Family of the people living in tea garden | The standarded of living improved due to financial stability earning after the placement. Shift from traditionally followed livelihood practice to skill oriented livelihood. | This observation is crucial as it highlights a positive shift in the socioeconomic status of youth and their families. Employment in the formal economy provides stable incomes, social security, healthcare, and career growth opportunities. This financial stability supports long-term planning, improves family livelihoods, and enhances the overall well-being of the community. | Youth Retention in Jobs | MIS Retention Data
| Youth from Schedule Tribe and Schedule Caste | They -changed from traditional way of livelihood working as Tea Garden Labour to skill based livelihood. This has developed the sence of empowerment among ST and SC community. | During Training and Placement | Among Schedule Tribe and Schedule Caste | The SC ST community in the tea garden has emarged with self-confidance and inspiring the youth from SC ST community. | Empowerment of Tribal Community: The centuries-old practice of bonded labor among the tribal community is gradually eroding as they recognize the importance of stepping out of their comfort zones. With a growing understanding of alternative livelihood opportunities, tribal and marginalized communities are embracing new pathways toward economic independence and social upliftment. | Providing opportunities to the youth belonging to Tribal Community. | MIS Data
| Youth in Communities | Change in Behavour: Youth shifted from passive participants to active promoters of the vocational program, sharing their experiences and encouraging peers to enroll and benefit from the training. Improved Confidence & Leadership: By referring others, youth gained confidence in their decisions and emerged as informal leaders, guiding and motivating their peers toward better opportunities. | After placement | In tea garden communities | Youth role models are emerging within each community, actively inspiring and encouraging others to explore vocational-led employment pathways. Their success stories highlight the value of skill development, motivating peers to pursue similar opportunities. By sharing their experiences, these role models foster a culture of learning, professional growth, and sustainable livelihoods, contributing to long-term community empowerment and economic resilience. | Catalyst for Social Change: Youth role models demonstrate that vocational-led employment is a viable path to success, breaking societal stigmas and encouraging more youth to pursue skill-based careers. Community Ripple Effect: Their influence increases vocational training participation, leading to higher employment rates, reduced poverty, and economic growth. Culture of Skill Development: These role models promote a culture of lifelong learning and skill development, fostering adaptability and workforce resilience. Supporting Sustainable Livelihoods: Vocational-led employment reduces reliance on unstable jobs, strengthening the local economy and promoting sustainable livelihoods. Impact on Future Generations: Youth role models inspire future generations to view vocational training as a respectable and achievable career path, shaping long-term community development. | Community Engagement: By actively involving the community in program activities, the program has created a supportive environment that celebrates the success of youth who choose vocational pathways, encouraging others to follow suit. Visibility of Success Stories: The program has highlighted the achievements of these youth role models through local events, social media, making their success stories widely known and inspirational to others. Alumni Experience Sharing: Alumni members have had a positive experiece in the program and have widely shared their experience within their friends and family networks. | MIS Data
| Tea Garden Women | Women from tea garden communities transitioned from exclusively domestic roles to becoming active participants in the formal workforce, increasing household income and financial decision-making power. | September 2024 - February 2025 | Across multiple tea garden communities in the region | Women's economic empowerment has transformed gender dynamics within households, with women now contributing significantly to family income and participating in financial decisions, leading to improved living standards and educational investments for children. | This change directly addresses gender inequality within tea garden communities where women traditionally had limited economic agency. The shift demonstrates progress toward gender equality and sustainable economic development for families, reducing vulnerability to economic shocks when depending on a single income. | Gender-specific mobilization campaigns that addressed cultural barriers; providing women-friendly training schedules; offering childcare support during training sessions; creating women-only batches for certain trades; connecting with female alumni as role models; and engaging with family elders to gain their support and permission. | Anecdotal evidences & case stories
| Education Providers | Local schools and colleges have begun integrating aspects of vocational training into their curricula, adapting teaching methods to include more practical skill development. | 2025-01-01 | Educational institutions in districts with tea gardens | Education institutions are evolving to meet changing workforce demands, creating better pathways between traditional education and vocational skills that prepare students for employment in emerging sectors. | This institutional-level change indicates systemic transformation in the education ecosystem, which will benefit future generations by providing more relevant education. It shows the program's influence extending beyond direct beneficiaries to affect long-term educational approaches in the region. | Sharing program success data with educational authorities; facilitating exposure visits of educators to training centers; providing teaching resources and curriculum support; building partnerships between schools and industry for student exposure. | Anecdotal evidences & case stories
British Asian Trust | VCPC member and community (Durga Baraik) | Identified and take action in a elopement case to sepearete two minor children. | Nov'24 | Chamurchi GP,Ambari Tg, Sansad number-I | Both the children separeted and re-intregrated in society wth the help of vcpc member . Boy started going school | Active intervention of VCPC member and community help in prevention of child marriage and early pregnanacy. | Strengthening of VCPC and oreint them about case management, Awareness meeeting within community aboupt child marriage and elopement and home visits of children | training sheet of vcpc member, meeting resolution of vcpc, home visit and case manangement sheet
| Parent - Bijay Bhuiya and Radha Kharia, Child - Mohit Bhuiya | Due to change in attitude of parents and child towards education leads to re-enrollemnt of child in school | Dec'2025 | Chamurchi GP,Ambari Sansad II beech Line | Children enrolled in school and attending school regularly | parents and children attitude change towards child's education. | regular home visit by animators, awareness meeting with parents and community | home visit
| VCPC | They Identified the CSA case in Garapara GP, Bhatkhawa TG and report the case to police | September'2024 | Garapora GP, Bhatkhawa TG, sansad XIV | Police intervente the case, victim was send to home and culprit in police custody. Child is now in school and preparing for Madhamik exam | VCPC member aresensitized regarding CSA cases and how to report it to higher authorities | VCPC members training regarding case mamangement. | VCPC member training sheet , VCPC meeting resolution, FIR document
| GPLCPC | Earlier only committee was formed but they were not awrae about their roles and responsibilites. | December' 2024 | Garopara and Malangi GP | GPLCPC members are aware about their roles and activitly conducting meeting at GP level. | They are conducting meeting at GP level | We trained GLCPC members and orient them about their roles and responsibilities | Training sheet of GLCPC, meeting resolutions of GLCPC
| VCPC | VCPC member reported the Kidnapping case of child to Police | September'2024 | Garapora GP, Bhatkhawa TG, Sansad XIV | Police reported the case and find the children within 3 days and send child to CWC. Child was send to home and mainstramed in school and preparing for madhayamik | VCPC members are confident about reporting case | VCPC members training regarding case mamangement. | VCPC meeting resolution, FIR copy, CWC hearing document
| VCPC member (ASHA, ICDS worker, PRI member) | VCPC member informed about Child marriage to CDPO, | Nov'24 | Garopara GP, Dima TG, Sansad IV | CDPO informed the case to police and police reached to house of children and prevented Child marriage. Child is now in school | VCPC members are becoming confident regarding reporting cases to higher authority | VCPC members training regarding case mamangement. | CDPO letter, VCPC resolution
| School teacher of Saudamini TG primary school and Huldibari TG primary school | Head teacher collaborate with our Aimator Rani Toppo, ASHA and ICDS worker and visited home of Dropout and irregular children to mainstreamed children in school | Jan'2025 | Malangi GP, Saudamini TG, Huldibari TG | Parents are oriented about the re-enrollment of children in school | School teachers are participating in enrollemnet drive and also involving VCPC member in this affort | regular visit to school and interaction with teacher and adressing problem of parents regarding enrollment of their children in school to school teacher | Home visit,VCPC meeting sheet which had list of children tracked during enrolment drive
| Community member (Subahas Lohara) and VCPC member | Ientified CNCP child name Aryan Lohar in his locality and reported it to our animator Anish Oraon and VCPC member about the vulnerable condition of child. Child was serverly malnurious and suffering from Tubercolosis | Nov'2024 | Malangi GP, Bharnobari TG, Line Dayal Line, Sansad XXI | VCPC member take action and did meeting for children and informed BMHO about the condition of child and BMHO provided ambulance for child and child admitted to Alipurduar Govt. Hospital | Due Active participation of community and VCPC child get immediate suport | Awaring community and vcpc about the case management | resolution and meeting sheet
| Child Collective children and remedial support centre children (Rupa Majhi, Binita Oraon, Devisha oraon) | They identified and bring a Dropout and Child labour surviour - Prianka Rajvanshi to remedial Support centre | Dec'2024 | Looksan GP, Ghatia TG, Sansad no.III | Dropout child labour survior continue attend the remedial centre and stop working. She was working Sikkim as child Labour. Now she is trying to make Adhaar card for getting admission in school. | Due to affort of children collective child stop working and get interest towards study. | Child collective meeting and session, awareness meeting with community, enrolement rallies and drive | child collective meetings, awareness programm meeting sheet, photograph
| Child -Priyanka Rajvansi (Dropout and child Labour Survivor | Bevahiour change about education and she stop working as child labour in Sikkim. She never told that she is working but now she express herself about continuing study and working in other state and also identifiying child like her. | Dec'2024 | Looksan GP, Ghatia TG, Sansad no.III | Her attitude towards education changes and stop working in skkim | When she visited garden she sometime attended our session and also interact with collective children | Child collective session/meeting, awareness session, remedial suppport centre | Child collective meeting/Session
| AWW- Laxmi Munda, AWH- Pinkey Mahali, VCPC member- Manoj Munda | They talked with the guardian of Priyanka Rajvanshi and oreint them about prevention of child labour and convice them to not send the Priyanka again to work in Sikkim | Dec'2024 | Looksan GP, Ghatia TG, Sansad no.III | Now piyanka attending remedial centre regularly and Her grand parents are trying to make her adhaar card so she can enrol in school in this acedamic session | Through the intervention of VCPC , atttitude of grand parents changes towards child labour and education | Regular meeting of vcpc member, vcpc members training on child protection issues | VCPC meeting register, VCPC training sheet.
| AWW- Asha Karmakar | Identify two dropout children - Kusmi Oraon and Suraj oraon and informed to our animators regarding it and reason for dropout as financial sitution of family was not good so they were unable to admit in school | July'24- Jan'25 | Chamurchi GP, Choonabhutti TG sansad XX | Now both the children are in school. They are also enrolled in acedamic sesion 2025. and Kusmi got Bycycle from school through Sobuj Sathi scheme | Timely identification and admission help in reducing vulnerablity of children and mainstreaming in school. Active participation of VCPC members | Interaction ICDS worker regulary, VCPC meeting, | Mainstreaming form, VCPC meeting regisiter
| VCPC member - ICDS worker Jhummi Kami, ICDS worker-Sabitri Mahato, ASHA- Rina Sarkar, ANM | They identified a elopement case in their sansad. Child name Sibika Oraon eloped with a boy in another play called Gairkata | September'2024 | Chamurchi GP, Newdooars TG, Sansad no-XXv | Timely intervention of vcpc member, Both the child separeted and noe Sibika enroled in schol | VCPC members are confident to report the case in police and interven the elopement case | VCPC training, meeting awareness regarding child marriage | VCPC meeting sheet, Stakeholder meeting sheet
| Coomunity member- (PRI member- Amit Munda, Parents- Banu Tirkey, Arti Tirkey, Subham Oraon, Child collective children- Riya Oraon, Priya oraon, Satyam Munda) | Mass rally for sensitized community to stop alocholism and consumption of Alchol in their community | Jan'2025 | Lookshan GP, Grassmore TG, sansad no-XXVIII, 4 No. Line | People stop make country Liquior (Handiya) at their home and consumption of alchol reduce and shops are also not selling any alcohol. | Alcholism are major factors to vulnerability in tea garden. Parents and community are taking initiative by their own to reduce it. | Community meeting , Parents meeting,child collective mmeting | Photo and video of rally, meeting sheet
| Parents- Hina ekka , Arti Bhattacharjee | They visited SSK 4 no Line graasmore School and monitored mid -day meal and also tasted the quality of food | Dec'2025 | Lookshan GP, Grassmore TG, sansad no-XXVIII, 4 No. Line | Now teachers are also taking care of quality of food and they also have mid-day-meal with children | Activte participation of VEC member and montoring visits to school | Parents meeting | parents meeting sheet, photo
| VCPC member- Teache- Parvin Kumar Jha, PRI member- Lalita Oraon | Dropout child name Mahesh Ahir whose financial condition was not good and he stay with grand parents and mother remarried to another person due to which he was not able to enrol in this academic session. VCPC helped him to get admission in school Balka Parimal Hindi High School in class X by writing a letter to school principal about his vulnerability and waving of fee | Jan'2025 | Banarhat GP-II , Redbank TG, Sansad n0-II | Now child is enroll in school | Active particpation of VCPC member and timely intervention help in enrolment of child in school and reduces the vulnerability by mainstreaming in school | VCPC training, awareness of VCPC member about their roles and responsibility | Letter given by VCPC to school teacher, VCPC meeting resolution
| Community and Panchay Member- Malati Naik | Community member and PRI member pressurized Trafficker named Pele Kale Gurung (Diana TG), , Anil Baman (Gandrapara TG) Sibani Oraon (Delhi - Talked over phn) to bring back a person named Krishna Routina who was sold in Shimla. | Jan'2025 | Banarhat GP-II, Diana TG, Sansad No IV | Timely intervention of community and VCPC person came home safely in February month | Active participation of community and awareness regarding human trafficking and unsafe migration | Awareness meeting on unsafe migration and Trafficking | VCPC meeting resolution, home visit
Kabil
Nazdeek | Tea garden workers | 1. Tea Grden workers from 7 tea gardens were able to submit multiple petitions for resolving local administrative issues, wage disputes, and employment conditions. | August, 2024 | In 7 tea gardens of Alipurduar and Jalpaiguri districts of West Bengal | a) Tea garden workers demand their rights and access benefits from public, private and civil society organisations. They register their grievances on non-realisation or non-receipt of rights, benefits and entitlement and raise their voice. b)Duty bearers (government officials/CSOs) address the concerns (gender discrimination, child endangerment, limited/no access to social entitlements, unreliable water supply, limited livelihood options) and ensure that the families receive entitlements and benefits, are able to exercise their rights and alternative livelihoods options are available. | It is significant as it contributes towards enabling workers to actively engage with administrative mechanisms, fostering greater awareness of their entitlements, and preparing them for long-term advocacy efforts. | 1. The team members from Durbar: a) conducted over 10 community meetings across various tea gardens to discuss worker grievances such as pending wages, Provident Fund deductions, and wage reductions. | Training reports and photoraphs from the training
| Tea garden workers and Paralegal Volunteers | 1. 08 Paralegal Volunteers, supported 17 tea workers in applying for identificatory documents such as birth certificates, AADHAR Cards, Election IDs, and for maternal and child health cash benefit transfer schemes. | 2024-11-01 | Elgin Tea Estate and Chengduar Tea Estate, Silchar, Assam |  | It is significant in that the PLVs were able to utilise the information and skills acquired through regular capacity building sessions, they have also developed a strong network within the communities, especially among women, and are abel to motivate the workers and their families to seek their rights and entitlements. | 1. Regular subject-matter and skill building trainings of PLVs; 2. Regular community meetings conducted by PLVs with the support of the organisational staff. | Training reports and photoraphs from the trainins and meetings; Monitoring and Evaluation visits
| Tea garden workers | 1. Tea garden workers engaged with the Tea garden employers to know about their PF status. 2. Tea garden workers sought assistance from civil society groups to connect digitally with the ATEPFO to know their PF status. | August-December 2024 | In 4 tea gardens of Bhergaon, Dist: Udalguri (BTR), Assam, India |  | It is significant as it contributes towards enhancing socio-economic indicators in the select Tea gardens. | Team members from UBSSB: a) conducted capacity-building programmes, where they trained tea garden workers on the entitlement frameowrk and the existing entitlements under different schemes. b) Two stakeholder meetings were held to promote sustainable community engagement and collaboration with decision-makers for improved socio-economic outcome such as poverty, illiteracy, and low wages. Participants included Aasha workers, Anganwadi workers, ACMS members, SHG members, teachers, health workers, student leaders, and social workers. | Training reports and photoraphs from the training
| Community women members & leaders | a) 3763 persons applied for work under NREGA. b) Women members of the community led and participated in a campaign to demand safety from the government at their workplace and otherwise | August- September, 2024 | In 7 tea gardens of Alipurduar and Jalpaiguri districts of West Bengal | a) Community and its leaders identify and raise voice on prevailing challenges related to gender discrimination, education, child protection, social entitlements, alternative livelihood pathways and water security. in different forums. b) Community and its leaders take-action to address challenges of gender discrimination, education, child protection, social entitlements, alternative livelihood pathways and water security. and reach out to public, private and CSOs for support/ guidance. | It is significant as it contributes towards enabling women members of the communicate to actively engage with administrative mechanisms, fostering greater awareness of their entitlements, and preparing them for long-term advocacy efforts. | Team members of Doorbar: a) conducted Capacity-building exercises for women workers were organized, focusing on legal rights, statutory entitlements, and participation in community representation. b) three Youth Paralegal Training sessions, engaging over 50 youths from tea garden communities on the topics of Indian legal systems, labor laws, gender rights, and Right to Information (RTI) drafting. c) Engaged with quasi-judicial and judicial grievance redressal processes, and support workers/communities through experts in such engagements. | Training reports and photoraphs from the training
Swaniti Initiative
Video Volunteers
ICLEI
Durbar
FPAI
Transform Tarde Prasari
ECS | STGs (Small Tea Growers) of Darjeeling | Participated in FGD sessions | 2024-04-01 | Darjeeling | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Contributed to increased awareness on sustainable agricultural practices among farmers | Conducted FGD sessions engaging local farmers | Attendance records from FGD sessions
| STGs (Small Tea Growers) of Jalpaiguri | Participated in FGD sessions | 2024-04-01 | Jalpaiguri | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Improved interaction and knowledge sharing among farmers | Conducted FGDs to encourage dialogue and participation | FGD session records
| STGs (Small Tea Growers) of Kalimpong | Attended RE Awareness Program | 2024-04-01 | Kalimpong | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Farmers began exploring RE solutions for agricultural needs | Conducted awareness programs on RE applications | Attendance records from awareness program
| Stakeholders in Darjeeling | Participated in District Level Stakeholder Meet | 2024-05-01 | Darjeeling | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Facilitated discussions on policy and interventions | Organized stakeholder meeting | Meeting minutes
| STGs (Small Tea Growers) in Darjeeling | Participated in FGD and RE Awareness Program | 2024-05-01 | Darjeeling | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Encouraged the adoption of sustainable farming methods | Conducted awareness sessions | Attendance records from FGDs and RE programs
| STGs (Small Tea Growers) in Jalpaiguri | Attended FGD and RE Awareness Program | 2024-05-01 | Jalpaiguri | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Farmers showed interest in learning more about RE | Conducted FGDs and awareness sessions | FGD session reports
| STGs (Small Tea Growers) in Rajganj | Attended RE Awareness Program | 2024-05-01 | Rajganj | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Farmers developed initial interest in RE applications | Conducted awareness programs | Attendance reports
| STGs (Small Tea Growers) in Darjeeling | Attended RE Awareness Program | 2024-06-01 | Darjeeling | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Farmers began exploring sustainable energy use | Conducted awareness sessions | Attendance records
| Dealers in Jalpaiguri | Attended Dealer Meet | 2024-06-01 | Jalpaiguri | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Encouraged supply chain actors to support RE adoption | Conducted Dealer Meet sessions | Meeting minutes
| STGs (Small Tea Growers) in Jalpaiguri | Attended FGD and RE Awareness Program | 2024-06-01 | Jalpaiguri | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Farmers started adopting RE-based agricultural methods | Conducted FGDs and awareness programs | Attendance records
| STGs (Small Tea Growers) in Darjeeling | Attended FGD and RE Awareness Program | 2024-07-01 | Darjeeling | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Farmers took steps toward adoption of new techniques | Conducted FGDs and awareness sessions | Attendance reports
| Dealers in Gorubathan | Attended Dealer Meet | 2024-07-01 | Gorubathan | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Dealers agreed to promote RE solutions | Conducted Dealer Meet | Meeting minutes
| STGs (Small Tea Growers) in Darjeeling | Attended Dealer Meet, FGD, and RE Awareness Program | 2024-08-01 | Darjeeling | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Increased demand for RE solutions among farmers | Conducted Dealer Meet and awareness sessions | Attendance records
| Stakeholders in Jalpaiguri | Participated in District Level Stakeholder Meet | 2024-09-01 | Jalpaiguri | Tea Garden workers adopt alternative livelihoods options, preferably, in the formal economy and in sustainable employment practices, with access to industry linkages, financial resources, and support systems, thus reducing their dependence on tea-gardens as their only source of income. | Stakeholders agreed on certain RE adoption strategies | Organized stakeholder meeting | Meeting minutes
| STGs (Small Tea Growers) and Business Owners in Jalpaiguri | Attended Meeting with Resort & Hotel Owners on RE Solutions | 2024-10-01 | Jalpaiguri | Tea Garden workers adopt alternative livelihoods options, preferably, in the formal economy and in sustainable employment practices, with access to industry linkages, financial resources, and support systems, thus reducing their dependence on tea-gardens as their only source of income. | Hotels and resorts showed willingness to adopt RE solutions | Organized meetings with business owners | Meeting records
| STGs (Small Tea Growers) in Jalpaiguri | Attended Solar Training | 2024-12-01 | Jalpaiguri | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Farmers gained practical knowledge on RE applications | Conducted Solar Training | Training attendance records
| Stakeholders in Darjeeling and Kalimpong | Attended District and State Level Stakeholder Meets | 2025-01-01 | Darjeeling & Kalimpong | Tea garden workers carry out participatory planning, adopt renewable solutions, and mitigation approaches to address climate change. Tea garden workers diversify their livelihoods and adopt climate resilient options. | Stakeholders developed strategies for broader RE adoption | Organized stakeholder meetings | Meeting minutes
Sanhita | Tea Garden Management | 1 tea garden constituted Internal Committee | 2025-01-01 | Banarhat Block, Jalpaiguri District, Dooars Tea Growing Region | Tea Garden Management created the redressal system | Constitution of IC is a step towards implementation of the Act 2013. The management is resposible for creating effective redressal mechanism free from sexual harassment | Dialogues with the Trade Unions, who worked as a pressure group; Sensitisation among women workers initiated discussions on the issue | Office Order of the Constitution of IC by Tea Garden Management
| Trade Union Leaders | 1 additional Central Trade Union collaborated with Sanhita to raise awareness among the tea garden women workers on the issue of SHW | 2025-08-01 | Naxalbari Block, Darjeeling District, Terai Tea Growing Region | 1. Issue of SHW got acknowledged for the 1st time in the Naxalbari Block of Terai 2. Women Workers broke their silence and started sharing their experiences of SHW | Trade Unions occupy a crucial position in the dynamics of the tea gardens and they represent the organised voices and flag the demands of the workers. Moreover, they can act as a safety net in crisis situations when a female workers complains against SHW. So change in attitude of Trade Unions and their acknowledgement of the issue is critical | Sharing the Situation Analysis Study findings on 14th March 2023 with 5 Central Trade Unions and continuous and persistent dialogues with them thereafter (April 2024 onwards). | Report of Sensitisation Sessions
| 8 Peers Leaders | 8 peer leaders from 8 tea gardens have knoweledge on the issue of SHW & the Act 2013 and disseminating information in their community | 1) A two-day training on Gender, SHW issue & Act during November 2024 2) A refresher training online during January 2025 | Banarhat Block, Jalpaiguri District, Dooars Tea Growing Region | 8 peers leaders have knowledge and are disseminating information in their community | The peer leaders are known faces among the tea garden workers, have access to the community, speak the local Shadri language, and are well-positioned to build trust and effectively communicate key messages. Their presence within the gardens ensures accessibility and dependability, making them ideal for carrying forward the awareness initiative. | Rigororus training and follow-ups | Report of Trainings | Module of Training | Photographs
| Women Workers | Women workers during orientation programs started understanding which behavious constitute SHW and some among them started sharing their experiences | Orientation Programs on 25th August 2024, and series of 14 Sensitisation Sessions during January 2025 | 8 tea gardens in Banarhat Block, Jalpaiguri District, Dooars Tea Growing Region & 4 tea gardens in Naxalbari, Darjeeling District, Terai Tea Growing Region | Women started breaking silence | Information is power | Information about their rights of a safe workplace, which was totally lacking previously | Reports of Sessions | Photographs

## Migrant & Unorganised Workers J
| Description of Change |  |  |  |  | Significance of change | Contributing Factors | Evidence
Partner | (Social actor - individual, groups, institutions, networks, community, organisation) | What did they do different? What was the change (Change in behaviour, relationships, actions, activities, agenda, policies, or practices) | When did it happen? (Should be after programme activities - date/month/year - specified) | Where did it happen? (Eg. Village / block / district; or - local, national etc) | Outcome Statement | Why is this observation of change noteworthy? How does it relate to the program vision and/or theory of change? | What do you think has contributed to this change? What, specifically, has the program done that might have contributed to this change? | Include links to any additional documentation or sources if relevant, e.g. news stories, speeches, meeting notes
DISHA
Dignity Alliance International (Jan Sahas) | Migrant Communities | 1. 4,81,700 Migrant households were registered in Jan Sathi app and gained awareness of various social security schemes, resulting in 6,33,479 successful applications and receipt of 5,37,849 benefits that improved their financial stability and overall well-being. 2. 75,323 migrant workers and their family members were sensitized and trained on safe migration and basic worker rights. | August 2021 to January 2025 | 1. Purba Bardhaman District (Ausgram -1, Mongolkote, Memari-1 and Khandoghosh blocks) 2. Nadia District (Krishanagar-1, Krishanagar-2, Kaliganj and Chapra blocks) 3. Birbhum District (Bolpur Sriniketan, Labpur, Rampurhat-2, Murarai-2 blocks) 4. Mursidabad District (Samserganj, Dhuliyan, Farakka, Suti-1 blocks) 5. Kolkata District (Bidhannagar Municipality - Ward No - 28, 29, 35, 36, 37, 38. Rajpur-Sonarpur Municipality - Ward No. 1, 21, 27, 28, 29, 30, 31. Kolkata Municipal Corporation - Ward No. 12, 21, 22, 23, 24, 28, 29, 31, 36, 109, 140, 141 Baruipur Municipality - Ward no - 10,11 Maheshtala Municipality - Ward No - 7,8,10,16, 18) Partnership Sites - HDFC, GPL and Tata Realty | 1. Migrant communities received benefits of various social security schemes and became aware on safe migration . | More than 50% Migrant workers have started applying for Social Security schemes. Most of the migrant workers or their family members are sensetized or trained through PDT/PAT to raise awareness on safe migration. | 1. Ensuring benefits through door to door approach, conducting applications in campaign mode, regular follow up with the concern departments and training migrant workers through PDT/PAT | Evidences are attached in a separate folder including screenshot of MRC dashboard, pictures of training attendance sheets and recording format of PDT/PAT.
| Migrant Communities | Migrant families were sensitized and made aware on various social security schemes, eligibility criteria, benefits available, assisting in application process, generating supporting documents required to apply for the schemes and where to submit applications. | August 2021 to January 2025 |  | 2. Migrant family empowerd to do their social security application ownself and submitted to the responsible department. Economic sheild to absorb the shocks | More than 50% of the migrant workers and their families gained understanding on the social security schemes, its application process, submission of the applications through officails channels and thus are accessing and availing their rights and entitlements. | 1. Through door to door approach and awareness camps MRC team has made migrant communities aware about social security schemes. | Evidences are attached in a separate folder consisting of pictures.
| Migrant Communities | Migrant families utilized the benefits of social security schemes to generate income and alternate livlihood, secure their future with insurance schemes, education support for children, health insurance and ration support for entire family etc. | August 2021 to January 2025 |  | 3. Migrant families are changing their lives with the benefits they recieved from social security schemes. | Migrant workers are applying and receiving benefits which are majorly covering part of their income and health shocks and created opportunities of improving life situations through different insurance and future opportunities. . | 1. MRC has organized many camps to facilitate the process of application on various social security schemes. 2. MRC team actively participated and engaged in Duare Sarkar camps to submit applications in bulk. | Evidences are attached in a separate folder consisting case studies.
| Migrant Communities | Some of the workers recieved benefits have been actively engaged in supporting and sensetizing the community in social protection and safe migration. | August 2021 to January 2025 |  | 4. Motivated households who had recieved benefits and the community volunteers support to get such benefits from the government and spread the information on safe migration among the community. | Sense of community ownership is being inculcated among the migrants workers and some of them have been emerging as community volunteers to carry forward the social protection for the community. | 1. Community members who are willing to help their communities and have potentials are trained by MRC team on social security schemes and safe migration. | Evidences are attached in a separate folder consisting pictures.
| Migrant Communities | 18,983 calls have been received in Mazdoor Helpline among which 2425 calls are from places where MRC is not operative. | August 2021 to January 2025 |  | 5. Mazdoor helpline number has significantly increased trust among the migrant communities. This trust is evidenced by the increasing number of calls received from both the MRC and the non MRC areas. | Migrant workers are accessing helpline number in case of disputes, immediate support and to seek information on social security schemes and workers rights. | Promotion of Mazdoor Helpline through IEC and wall paintings in hot spots, display at Govt. Departments, PDT/PAT. | Evidences are attached in a separate folder consisting screenshots of CMS dashboard, excel for data bifurcation and pictures.
| Industry Partners | Organized total 164 camps with the support of employers including awareness camp - 96, Social Security Camps - 57, IPPB Camp - 11, benefitting a total of 2282 workers. | August 2021 to January 2025 |  | 6. In partnership site, employers are sensetized to support migrant workers to apply on various social security schemes so that workers can access social security benefits and aware about the entitlements. | Partners are now supporting the migrant workers by allowing them to participate the awareness training of MRC's and attending IPPB camps for creating supporting documents and social security camps for submitting applications. | 1. MRC through constant advocacy and sensitization of industry partners brought significant changes to the mindset of employers. 2. IPPB and social security camps have been organized at the worksites to better facilitate the workers. | Evidences are attached in a separate folder consisting pictures.
SEWA Bharat | Migrant women workers from Murshidabad & Malda | Attended registration camps, provided required documents, and completed digital registrations. |  | Murshidabad & Malda | Over 1,500 migrant workers now have formal identification and access to schemes (health, housing, skill training). | Ensures inclusion in social safety nets, reduces vulnerabilities during migration, and opens pathways for safer migration. | SEWA Bharat’s outreach campaigns, support from SSKs, and partnerships with panchayats and labour department. | Registration records, screenshots from portals, attendance sheets from camps.
| Migrant workers (Malda to Delhi migration corridor) | Participated in participatory mapping exercises and identified safe transport, housing, and workplaces at destination. |  | Malda & Delhi | Safer migration pathways identified, reducing risk of trafficking and labour exploitation. | Builds safer mobility practices and improves knowledge among migrant workers about risks and rights. | Migration corridor mapping workshops, consultations with destination-based SEWA teams, digital tools training. | Migration maps, testimonies, photos from mapping workshops.
| Beedi workers (Murshidabad & Malda) | Mobilised, held bipartite meetings with Mahajans (middlemen), and collectively bargained for better rates. |  | Murshidabad & Malda | 12% wage increase agreed and documented across 8 blocks. | Demonstrates the power of collective bargaining and strengthens the organising base of SEWA. | Training on negotiation skills, evidence gathering on cost of living, peer support from other SEWA collectives. | Minutes of negotiation meetings, wage rate circular, photos from wage meetings.
| Adolescent girls from migrant worker families | Attended awareness sessions and received support to re-enroll in local schools. |  | Murshidabad & Malda | Increased school retention rates, reducing dropouts among adolescent girls. | Reduces vulnerability to early marriage and trafficking, improves long-term earning potential. | Parent sensitisation meetings, school enrolment drives, support with scholarships and learning materials. | School enrolment data, attendance lists, photos from enrolment drives.

## Indigenous Communities Journal
Partner | (Social actor - individual, groups, institutions, networks, community, organisation) | What did they do different? What was the change (Change in behaviour, relationships, actions, activities, agenda, policies, or practices) | When did it happen? (Should be after programme activities - date/month/year - specified) | Where did it happen? (Eg. Village / block / district; or - local, national etc) | Outcome Statement | Why is this observation of change noteworthy? How does it relate to the program vision and/or theory of change? | What do you think has contributed to this change? What, specifically, has the program done that might have contributed to this change? | Include links to any additional documentation or sources if relevant, e.g. news stories, speeches, meeting notes
Association for India Development
Centre for People's Forestry | Farmer Group (TFSC): Male Farmers, Female Farmers | Started agroecological practice, crop diversification, water resource development and nutritional security amoung male and female farmers. | July 2024 to January 2025 | 25 Project Village in Ranibandh Block, Bankura District | 1. A total of 925 paddy farmers are adopting the System of Assured Rice Production (SARP) method across 977 bighas (326 acres) of land, with training provided on the use of bio-pesticides and bio-fertilizers. Additionally, 666 bighas of fallow land have been brought under cultivation with maize, black gram, and red gram. 2. 220 acres (662 bighas) of land were cultivated with mustard, benefiting 670 farmers, while 206 acres (619 bighas) of land were used for food crops (cereals and pulses), also benefiting 670 farmers. Furthermore, 69.33 acres (208 bighas) of land were cultivated to vegetable cultivation, benefiting 323 farmers, with crops including cabbage, tomato, and cauliflower. 3. 20 mobile vermicompost units were promoted, which will yield results, and 2 SMC structures were desilted and repaired. 4. The dietary habits of the community are shifting, with 400 farmers now growing a variety of vegetables in their household yards, thereby enhancing food security at the household level. 5. The transition to agroecological practices was facilitated through Farmer Field Schools and 51 demo plots, training 2,642 individuals on agroecological practices, crop-specific techniques, and crop diversification. Additionally, 2,462 farmers were trained in the preparation and application of Jeevamrutham, Neemastram, Agniastram, and Ganajeevamrutam, with 342 farmers actively using these methods. | In West Bengal Paddy is the main crop and use huge level of pesticide, farmers are now shifting towards crop diversification and chemical free farming. This is becoming possible because of the Tribal Farmers Service Centre/ CBO getting established and they are adopting and spreading awareness about the agro ecological practices to other farmers. | Input support and handholding support and training to farmers through demo plots and FFS have paved the way for this change. Motivating the communities through shramdan and financial contribution had resulted in communities owing of the project. | Photographs of fields. Maintained crop production data in excel and registered.
| VCG: Project Community like AWC Worker, Asha Worker, School Teachers, Men and Women in Village | Ensure all eligible individuals can access their entitlements and seek support for community needs. | July 2024 to January 2025 | 25 Project Village in Ranibandh Block, Bankura District and 12 village in Sandeshkhali I & II Block, North 24Pargana District | 1. Facilitated enhancing of social security through petitioning of 180 individual entitlements. Out of 180 individual entitlements 132 sanctioned. The individual entitlements included (caste certificate, old age pension, Lakhi bhandar, Swastha Sathi, Widow pension, Krishak Bandhu) 2. To enhance the standard of living petitioning of 46 community needs out of which 3 got sanctioned. The community needs included (Pathsree, Soakpit, ICDS repair, Tubewell. Street light, Jal Jeevan Mission) 3. After creating awareness about FRA Act and promoting the farmers through awareness meetings in villages 112 farmers came forward to apply for IFR titles. IFR claims are in process for submission. | In tribal areas the last mile of delivery of services is a challege unless communities are trained on accessing their rights and availing various schemes they will be deprived of better aminities. | Building awareness and training project communities on various schemes and in availing government services and entitlements. Duare Sarkar Camp, organized by the West Bengal Government, helps the community to submit petitions at the doorstep. Organise a Aadhaar Camp for new and correction of Aadhaar card through a enrolment agency. | Receiving copy of community petition and picture of filled format of individual petition.
| TFSC and VCG Group: Landless and resource poor and women farmers | Access to alternative livelihoods | July 2024 to January 2025 | 12 Project Village in Ranibandh Block, Bankura District | 1. Support was provided to 140 landless farmers and single women through the distribution of ducklings, which they are now raising. This initiative will offer monetary benefits and provide eggs for consumption. 2. 54 women have been trained in Sal leaf stitching and using 12 Sal leaf stitching machines across 3 centers/villages. Market linkages with the local community are being explored, and the women are now earning between 1,000 to 1,500 per month through the value-added Sal leaf products. | Single women and landless farmers are vulnerable and they need extra support to enhance their income. | Technical support for rearing and vaccination purposes. Contacted the government and attempted to bridge the gap between the community and the department. | Quaterly check status of livestock
Sign of Hope + DRCSC | Indigenous communities in the village | Applied and followed-up regarding important identity documents (ST certificates, Aadhaar cards etc.), and approached the Gram Panchayat through a group deputation to request for information camps about relevant govt. schemes. As a result, local Gram Panchayats and Block offices have been mobilized to organize varioussuch information camps. The communities have also been instrumental in spreading the knowledge and awareness gained to their peers within and beyond their village, helping more people to access these facilities. | Aug 2023 - Ongoing | Kakdwip, Kultali, Sandeshkhali I and Hingalganj Blocks in the Indian Sundarbans | Since August 2023, indigenous communities in the Indian Sundarbans have been able to enhance their access to the available governement schemes and entitlements by effective engagement with the govt. line departments and PRI functionaries through strengthening village level women/youth groups, community institutions in the operational villages, and have increased their participation in local governance (Gram Panchayat etc.). Since August 2024, community visits to relevant government departments to seek information and assistance in accessing government benefits have increased, with no hesitation on their part. | It contributes to our outcome of strengthening indigenous communities' govt. participation and access to rights and govt. schemes with the participation of women. Through these efforts, the communities have become aware of their needs and govt. measures which can address some of those needs. Indigenous women have become proactive in accessing their rights and govt. facilities. Several community members who had applied to the Tribal Welfare Dept. for caste certification have received their certificates. In addition now PRI members, BDO and other relevant govt. officials have begun to train their focus on developmental initiatives at the village level so that nobody is left behind. The communities have continued to visit govt. camps, departments, and other relevant offices as needed, with no hesitation. | 1. Team members of DRCSC and LRRM help the indigenous communities apply for their identity documents and follow-up with the local government to obtain these documents of the indigenous communities; and 2. Team members of DRCSC and LRRM provide technical support and guidance to the groups to prepare their application to the Gram Panchayat with their requests. Team members from DRCSC and LRRM have provided technical support and guidance to the groups in preparing their applications to the Gram Panchayat for their requests. | Annex-1
| Indigenous communities in the village | The indigenous communities received training in, and began to practice, climate resilient agriculture (using indigenous seeds, organic fertilisers and organic IPM, single stick paddy cultivation technique, maintaining nutrition gardens in their backyards etc.), and nutrition gardening following regular weather forecast and agro-advisory issued by the project's Information Hubs. They have begun to cultivate indigenous varieties of crops using seeds they received through the project and have also developed seed banks at the Information Hubs for future use. Seeds are also being saved at the household level as communities have become aware of their importance in sustainable agriculture. The communities have also began participatory shore protection through mangrove plantation and maintenance (using terracotta rings). Fishery/ Aquaculture trg | Apr 2023 - Ongoing | Kakdwip, Kultali, Sandeshkhali I and Hingalganj Blocks in the Indian Sundarbans | Since April 2023, the indigenous communities have enhanced their climate resilience through climate-adaptive practices of agriculture and allied livelihood and sustainable natural resource management at the village level for food and income security. Traditional paddy and pulses, are being cultivated organically, and organic fish farming/aquaculture is alo being done with organic inputs. Farmers also preserving their seeds. | It contributes to our outcome of enhanced climate resilience among the indigenous communities through climate-adaptive practices of agriculture and allied livelihood and sustainable natural resource management at the village level for food and income security. People preserving indigenious seeds at the household level has contributed to an increase in their control over farming. Women's decisionmaking agency has increased even in matters of agriculture, especially with regard to crop selection. Organic nutrition gardening has brought about a major positive change in the communities' food habits and nutrition intake as they now consume chemical-free produce and more vegetables and fruits than they did before. This has improved food and nutrition security in the project villages. They regularly consume indigenous varieties of rice, pulses, animal protein, and a variety of vegetables, all organically grown on their own farms. | 1. Team members of DRCSC and LRRM provide training and handholding support in organic farming and nutrition gardening to the indigenous communities; 2. Team members of DRCSC and LRRM provide indigenous seeds to the communities; 3. Team members of DRCSC and LRRM provide regular weather foreecasts and agro-advisories; 4. Team members of DRCSC and LRRM provide wage, some materials (terracotta rings) and technical support to the communities for mangrove plantation through participatory shore protection. | Annex-2https://soundofsilencesundarban.com/2023/07/11/participatory-planning/ Annex- 2
| Indigenous communities in the 8 project villages | The indigenous communities were encouraged to preserve their rich linguistic and cultural heritage and take steps to arrest the loss of their language by ensuring that the children and youth learn their mother tongue. The communities were also encouraged to document their traditional song and dance performances on auspicious ocassions through photos, videos and audio recordings, which served as an encouragement to them, especially the younger generations, to practice the oral and performative aspects of their culture, which is also expected to contribute to improved mental, social, cultural and overall wellbeing of the communities. Women from the communities were provided training to provide informal mental health support within their villages since the mental healthcare framework in the Indian Sundarbans is extremely poor and largely inaccessible to these communities. | Oct 2022 - Ongoing | Sundarbans Blocks Kakdwip, Kultali, Sandeshkhali I and Hingalganj | Since Oct 2022, the voices of the unheard indigenous communities in the Sundarbans are being strengthened through preservation of their linguistic and cultural heritage, and representation of their challenges and needs on public platforms (Sound of Silence project website, social media, photovoice and publications) | It contributes to our outcome of strengthened voices of the unheard indigenous communities in the Sundarbans through advocacy with govt. line depts., preservation of their linguistic and cultural heritage, and representation of their challenges and needs in public platforms (Sound of Silence project website, social media, photovoice and publications). The communities are actively celebrating their cultural heritage by commemorating World Indigenous Peoples' Day on August 9, 2024, and regularly performing music within their communities using dhamsa and madol provided by DRCSC and LRRM. These traditional percussion instruments hold deep cultural and spiritual significance for the tribal communities, serving as a vital part of their rituals, festivals, and social gatherings, reinforcing their collective identity and ancestral traditions. | 1. Team members of DRCSC and LRRM encourage the communitites to preserve their unique linguistic and cultural identity; 2. Team members of DRCSC and LRRM provide training to women of the indigenous communities to identify and provide informal support for mental health challenges in the village; 3. The project website and social media maintained by researchers from DRCSC and LRRM are updated with information and materials emerging from community interactions about community issues; 4. The team members of DRCSC and LRRM provide photovoice training to the indigenous youth to enable them to represent their lives and experiences through photovoice materials. DRCSC and LRRM provided musical instruments to the communities and encouraged them to continue celebrating their cultural heritage, speak their mother tongue, and pass it on to the younger generation. | https://soundofsilencesundarban.com/2023/06/21/community-perceptions-of-mental-health/ https://soundofsilencesundarban.com/2023/03/19/insights-from-participatory https://soundofsilencesundarban.com/2024/10/29/celebrating-the-international-day-of-the-worlds-indigenous-peoples-in-the-sundarbans/
| Indigenous women in the villages | Indigenous women formed mutual cooperation groups (MCGs) to undertake the project activities. They began to take decisions related to livelihood decisions (particularly agricultural practices), and have begun to contribute directly towards decisionmaking to improve the families' food and income security. They have also begun to receive training in identifying their own and others' mental health needs and providing informal mental health support to improve the communities' overall wellbeing. | Apr 2023 - Ongoing | Sundarbans Blocks Kakdwip, Kultali, Sandeshkhali I and Hingalganj | Since April 2023, the agency, decisionmaking capacity and overall wellbeing of the indigenous community women are being strengthened. | It contributes to our outcome of empowering inidgenous women by improving their agency, decisionmaking capacity and overall wellbeing. | 1. Team members of DRCSC and LRRM provide capacity building support to the MCGs for decisionmaking, climate-resilient agriculture, and informal mental healthcare; 2. Team members of DRCSC and LRRM encourage the MCGs to take steps to reduce substance use and domestic violence in the villages. | Annex-4